|  | Original Milestones | Date |
| --- | --- | --- |
| 1 | Farmers, extension agents, and researchers (beneficiaries) learn about project and provide their input and reactions via introductory article, feedback survey, and comments on Rodale Institute’s (RI) website. | May 2010 |
| 2 | RI research staff install iButton temperature and humidity sensors, sample cover crop biomass and ground coverage at RI plots (all years) and farmer collaborators’ (FCs) plots (2011 and 2012) | May/June 2010, 2011, 2012 |
| 3 | RI research staff collect data on weed density, diversity, and OM inputs. | June/July and August/September 2010, 2011, 2012 |
| 4 | RI research staff and FCs collect and weigh both total and marketable yield bi-weekly or as needed in each treatment plot at the RI and on collaborating farms. | July-September 2010, 2011, and 2012 |
| 5 | Regional beneficiaries take part in first project Field Day at RI, presenting vegetable/cover crop trials and equipment demonstrations. | July 2010 |
| 6 | RI research staff work with FCs to plan/ establish plots, plant cover crops, and sample soil | August/September 2010, 2011, 2012 |
| 7 | RI research staff process, send out for analysis and perform in-house analyses on soil samples | August/September 2010, 2011, 2012 |
| 8 | FCs, select extension agents, and researchers meet with RI staff to review 2010 data (including FC costs and savings) and plan for 2011. | January 2011 |
| 9 | Beneficiaries review article summarizing 2010 field data, activities, and plans for 2011 on RI’s website. | January 2011 |
| 10 | 2010 Field Day and conference attendees surveyed to assess adoption of practices and additional information needs. | January-March 2011 |
| 11 | Regional beneficiaries attend second Field Day, hosted by FC | August 2011 |
| 12 | FCs, select extension agents, and researchers meet with RI staff to review 2011 data and plan for 2012. | January 2011 |
| 13 | Beneficiaries review article summarizing 2011 field data, activities, and plans for 2012 on RI’s website. | January 2012 |
| 14 | Beneficiaries and the public learn about project research and recommendations via presentation at annual winter conference | February 2012 |
| 15 | 2011 Field Day and conference attendees surveyed to assess information needs and adoption of practices. | March 2012 |
| 16 | Regional beneficiaries attend third Field Day, hosted by FC | August 2012 |
| 17 | Beneficiaries and the public receive 30-page vegetable production manual, available in print and on-line as a pdf. | December 2012 |
| 18 | Beneficiaries read final project summary article on RI’s website. | January 2013 |
| 19 | Researchers and extension agents review scientific project summary via peer-reviewed journal article(s). | submitted January 2013 |