| Activity | Action Steps/Status |
| --- | --- |
| Year One- January 2009-December 2009 |  |
| Design community workshops that connect farmers, Extension staff, nonprofits, | Meetings held with the following to determine interest in community workshops: - Institute of Agriculture and Trade Policy - Minnesota Sustainable Farming Association - University of Minnesota Extension-Health and Nutrition Local Foods Work Group - University of Minnesota Extension-Health and Nutrition School Nutrition Work Group - Healthy Eating Coalition – a statewide group composed of members from - the Minnesota Departments of: - Education - Health - Agriculture - Human Services - The University of Minnesota Extension |
| Provide at least 2 Webinar (UMConnect) Trainings on implementation of Farm to School programs using the U of M Online Farm to School Toolkit on the MISA website. This toolkit provides MN specific tools for local food menu planning, food production, purchasing/sourcing and nutrition messaging in schools. As part of the University of Minnesota, we have access to an excellent virtual meeting program that allows for visual connection, white boards, discussion rooms, notes, polling, and a variety of other technologies that have been found to greatly enhance the efficacy of hosting virtual meetings and trainings. We will have unlimited access to UM Connect during the course of this project and can also make this available to the larger Farm to School community as needed. | Toolkit Trainings/Presentations (Trainings were done in person since the opportunity was presented and face to face is the ideal way to train) - Minnesota School Nutrition Association Directors Meeting- Chaska, MN, May 2009, 88 attendees - Minnesota School Nutrition Association Annual Meeting –Duluth MN August 2009, 60 attendees - Minnesota School Nutrition Association Nutrition Conference October 2009 Chisago City 100 attendees |
| Offer training at the NEP Annual Conference on successful local and national programs that reconnect food insecure children and communities to the local food system through community and school gardens, farm visits, and school lunch programs. This grant would facilitate bringing in speakers from the National Farm to School network and the Sustainable Farming Association. | - Training provided to Extension Educators and Program Coordinators by Sara Tedeschi, Great Lakes Farm to School Network (GLF2SN), July 2009, 30 attendees - Training provided by Amanda Archibald, Field to Plate and Lynn Mader Farm to School Coordinator Alexandria MN, 120 attendees |
| Survey the University of Minnesota and Community Partners to determine what types of Farm to School activities are currently being done by NEP educators and within other areas of Extension and the broader University and to determine what areas of further education and program development are considered most important. | - Nancy Taft, MPH graduate completed her thesis, “Growing a Farm to School Network,” utilizing results of the survey with NEP educators. |
| Investigate the potential to integrate Farm to School messaging and programs within existing Simply Good Eating curriculum. | - Piloted Farm to School NEA Training April 2009, 24 attendees - Established a NEP task force to identify current efforts of F2S with the SNAP-Ed program - Attended National F2S conference in Portland (2009) and Detroit (2010) to identify educational materials that could be used for NEP program |
| Year Two- January 2010-December 2010 |  |
| Conduct six Regional Local Foods Training and Networking Workshops based on regional needs and specific interest areas. Local farmers, educators, community groups, school wellness committee members, and Extension staff will be convened. Extension NEP staff and the U of M Regional Partnerships will help organize and coordinate these meetings along with NGO and community partners which will include local farmers and farm organizations. | - Eight workshops took place from February to November 2010 - 2/16/10: Morris - 3/23/10: McIntosh - 4/7/10: Baxter - 4/27/10: Windom - 4/28/10: Stewartville - 4/29/10: Cloquet - 11/30/10: Mahtomedi - 12/2/10: Chaska |
| Integration of Farm to School and local foods information into existing and new curriculum development and coordination and collaboration between cafeteria and classroom activities | - Farm to School has been incorporated in both the teacher and food service guides’ of the Go Wild curriculum, April 2010 - Two Go Wild webinars were completed in May 2010 with Simply Good Eating staff. |
| Present sessions by Regional NEP groups at the 2010 NEP Annual Conference offering hands on information about reconnecting children and communities to the food system through mini-sessions, displays, and make-and-take-sessions. These sessions will be determined by the outcome of the regional networking workshops. Sessions could include: Hands on implementation of the newly developed U of M Online Farm to School that offers modeling of menu planning, food production and purchasing practices that utilize local, sustainably produced foods; implementation and education in connection with family community gardens to increase access to whole/fresh minimally processed foods; experiential education opportunities with farm visits and gardening experiences, cooking and food skills and food preservation training | - Met with Simply Good Eating’s Program Coordinators during their two-day meeting to discuss the integration of Farm to School into the CNEs work plan and activities, July 13, 2010. - On September 16, 2010 at the Simply Good Eating Conference a session on “The Farm to School Movement” occurred. The Farm to School Coordinator was joined by Donna Anderson, Wadena County; Lynn Lokken, Lac Qui Parle County; Denise Pollard, Morrison County; Nancy Winter, Kandiyohi County; June Sorensen, Faribault County - In addition to reviewing the Farm to School toolkit, each of five CNEs above shared their personal stories with the audience including: 1) Farm to School displays utilized in the cafeteria, 2) Farm to School in a basket, 3) youth gardens, 4) taste testings, and 5) school wellness committee involvement; 30 attendees - Other workshops at the 2010 Simply Good Eating conference included: 1) learning to grow nutrient dense foods in a northern climate, 2) water bath canning, 3) utilizing a smart board to connect kids with agriculture and food. (See Simply Good Eating conference brochure attached) |
| Provide at least 2 Webinar (UMConnect) Trainings on implementation of Farm to School programs using the U of M Online Farm to School Toolkit on the MISA website. This toolkit provides MN specific tools for local food menu planning, food production, purchasing/sourcing and nutrition messaging in schools. As part of the University of Minnesota, we have access to an excellent virtual meeting program that allows for visual connection, white boards, discussion rooms, notes, polling, and a variety of other technologies that have been found to greatly enhance the efficacy of hosting virtual meetings and trainings. We will have unlimited access to UM Connect during the course of this project and can also make this available to the larger Farm to School community as needed. (Activity from Year One-January 2009-December 2009) | Region; Location; Meeting date; Time. South East; Rochester; Aug 24; 1:00-3:00. South Central; Mankato; August 19; 12:30-2:30. South West; Worthington; June 8; 1:00-3:00. West Central; Morris; August 25; 9:30-11:30. Central; Willmar; Sept 29; 9:00-11:00. West Moorhead; Moorhead; Sept 28; 10:00-12:00. Northwest; Thief River Falls; Sept 27; 10:30-12:30. North Central; Brainerd; Sept 1; 1:00-3:00. North East; Grand Rapids; Sept 2; 10:00-12:00. East Central; Mora; Sept 3; 9:30-11:30. West Metro; Minneapolis; Aug 23; 9:15-11:00. East Metro; East St. Paul; Oct 11; 1:00-3:00. The table above details meetings with each of the 12 Simply Good Regions. Trainings were done in person as the opportunity was presented and face to face is the ideal way to train.. |