Plan of Work

| Who | What | When |
| --- | --- | --- |
| Pat UNHCE Specialists | Consult to approve the final design of the system | April 2013 |
| Pat Hired professionals | Purchase materials Installation | May to September 2013 |
| Pat, Employees Kelly McAdam, other UNHCE staff | Monitor System Production of Perennials Project Check-in | January to April 2014 |
| Pat UNHCE Staff, Agriculture Engineer (Univ. educator) | Twilight Meeting hosted by Petal Pushers Farm | March 2014 |
| Pat Kelly McAdam | Final project wrap-up Publish results and system design, specifications and cost | July 2014 |
| Pat | Begin to experiment with other compost materials (woodchips, brush) | August 2014 |
| Pat UNHCE Staff | Share results at NH Small Family Farm Conference | January 2015 |
| Pat UNHCE Staff | Compile results from further experimentation and publish | March-April 2015 |