Naturally Grown Transition Timetable 2014

(Revised 5/16/14  via Rufus Isaac Comments)

| Date | Planned Activity | Modifications | Comments |
| --- | --- | --- | --- |
| March-April | Mechanical weeding for mummy berry spore, grubs and weed control |  |  |
| April-May-June | - Track degree-days - Scout mummyberry shoots - Apply Regalia at 10-14 day intrvls |  |  |
| April | Apply cornmeal to control fungus, fertilize |  |  |
| May 1 | Apply SulferX |  |  |
| April 20 | Deadline to complete pruning |  | completed |
| May to August | monitor pests |  | - fruit worm – in field - SWD |
| May 1 | Track degree days for fruit worm/maggot Apply dish soap, fish emulsion mix / mechanical weeding |  |  |
| May 15-July 30 | Repeat fish mix/soap |  |  |
| July-August | Apply Entrust for SWD |  |  |
| Aug 30 | Apply Regalia |  |  |
| Sep | Mechanical weeding/corn meal w/ pine needles |  |  |
| Sep | Mechanical weeding w/pine needle |  |  |