FW10-056

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| TASK | PROJECTED COMPLETION DATE AS OF JAN. 26, 2011 Progress Report | ACTUAL DATE KOKOLULU FARM | ACTUAL DATE LOKAHI FARM | ACTUAL DATE KMHF | MAX AMOUNT VARIATION  From projected date | AMOUNT VARIAION AMONG 3 FARMS |
| Plant stock & cover crop | March-April 2011 | 4/--/11 | 5/--/11 | 3/29/11 | 1 month | 2 months |
| Plot #1 is control : no weed cloth |  | KF put weed cloth down on control in April 2011 due to a miscommunication. The other farms used mulch and weeding. |  |  | none | N/A |
| Plot #2 “mow cover crop” and weed cloth down | July 2011 | 9/--/11 | 1/2/12 | 10/12/11 | 7 months | 4 months |
| Plot #3 “Mow cover crop” and harvest | Nov. 2011 | 2/8/2012 projected date: 4/21-28/12 | 2/8/2012 projected date: 4/21-28/12 | 2/8/2012 projected date: 4/21-28/12 | 6 months | Projected: none |