## SARE Acknowledgement
This material is based upon work supported by the National Institute of Food and Agriculture, U.S. Department of Agriculture, through the Northeast Sustainable Agriculture Research and Education program under subaward number FNE20-953.

## Work Plan
Date |  | Task | Estimated Hours | Mileage
Nov / Dec
| Copy and update Organizer's Workbook |  | 1
| Reach out to vendors - confirm discounts & pricing |  | 4
Confirm previous vendors
Pursue new vendors / wish list items
Update information on vendor tab
| Review info & expectations with distribution sites |  | 2
Revise (distribution site tab) and send by email; schedule call
Confirm pickup weekend dates
Update information on site tab, if any changes
| Check in with fiscal sponsor; confirm proces/terms for this year |  | 0.5
| Update website with dates / new policies, "coming soon" |  | 1
| Initial outreach, i.e., "the bulk order is coming - preview catalog" |  | 0.5
Jan 1-15
| Update catalog pricing |  | 15
Enter discounted (price to program) cost for all vendors/items
Enter comparative catalog price + shipping cost for all vendors/items
Determine bulk order price for all vendors/items; when finished, copy paste "paste values only" to remove equations and small decimals
| Update catalog functions |  | 10
participant information
participant agreements
opt ins
check that subtotals and discounts calculate correctly
set up / test order consolidation filter
test how orders input into master sheet
update formatting / style
any other revisions
| Update website with form links; final information revisions |  | 0.5
| Outreach - "orders now open" |  | 1.5
Draft and include newsletter / updates
Include very clear text information on pickup dates, etc
Jan 15-Feb 12 | Create Master Order Sheet |  | 1
| Input orders and invoice as they come in |  | 25
| Light outreach, reminders, and participant communications |  | 3
| Follow up on unpaid invoices |  | 1
Feb 12-15 | Close orders, sort, check, and send to vendors immediately |  | 20
| Confirm wish list items, send follow up invoices and notices that orders will go through |  | 2
Check in with sites - volume expectations
Feb 15-Mar 5 | Vendor follow up; review, confirm, and pay for orders |  | 10
Mar 5 - Mar 15 | Confirm and collect shipping information |  | 5
| Final site check in, with shipping details and final info (email or call) |  | 1
| Purchase supplies: clipboards, sign paper, sharpies, rachet straps, etc |  | 1
| Generate pack-out lists and assemble site packets; send or deliver |  | 10
Pickups per site - alphabetical list with contact
Pickups per site - organized by pickup window
Pack out list for each vendor per site
Copy of each order
Exit tickets
Shorts / errors sheet
W9 for site
Print and digital copies of all
| Site visits & support |  | 8 | 100
| Pickup reminder & info emails to all participants |  | 2
Email; CC site managers
Request to schedule time block if they have not done so
Overhead photos of site - where to enter / exit / pick up
Day of Contact
Prepare for your volume of items (consider 2 vehicles, rented trailer)
Mar 16-20 | Site visits & support |  | 15
| Collect and communicate backorder information |  | 15
| Compile exit ticket responses |  | 1
Mar 20 - April 15 | Communicate with vendors and farms re: backordered items |  | 5
| Prepare materials for backorder day |  | 1
| Send backorder day confirmation email |  | 1
April 15 - May 1 | Site visit: pick up unclaimed items, deliver payment and gifts to sites |  | 6 | 100
Collect any final backorder / refund information
| Issue refunds |  | 3
| Wrap up, reporting, and bookkeeping |  | 8
May - Nov | Strategic & development work, as needed

## Vendors & Orders
Vendor Name | Supply Category | Contact Name | Phone | Email | Reached Out? | Confirmed Discount Terms? | Updated Catalog - Bulk Price? | Updated Catalog - Price to Members? | Updated Catalog - Retail price comparison? | Discounts & Pricing Summary | Order lead time needed | Sent Order? | Confirmed order? | Reviewed order? | Received Invoice? | Sent Payment? | Payment Info: | Send Check To: | Invoice Location: | Check # | Amount - Site 1 | Amount - Site 2 | Total Sum | Confirmed Delivery? | Planned Delivery Date | Estimated Pallets - Site 1 | Estimated Pallets - Site 2 | Arrived? | Shipping Info: | Revenue - Site 1 | Revenue - Site 2 | Net on order | Percent markup
This Year's Confirmed Vendors
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE
Past / Future / Non-Active Vendors

## Distribution Sites
Distribution Site Names |  | Shipping Address | Contact Name | Email | Phone | Confirmed Participation? | Shared & confirmed written expectations? | Check in - after orders close | Check in - final, before pickup weekend | Delivered packets and supplies | Total Sales per site | # of pickups per site | Average Order Size | Pallets Per Site | Issued payment? | Collected 1099? | Collected Invoice? | Site Fees + Labor | Costs as Percent of Revenue | 2.5% of revenue | Customer satisfaction survey average: Overall / Site | Debrief Call
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | #DIV/0! |  | FALSE | FALSE | FALSE |  |  |  |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | #DIV/0! |  | FALSE | FALSE | FALSE |  |  |  |  | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  |  | #DIV/0! |  | FALSE | FALSE | FALSE |  |  |  |  | FALSE
ROUND 1: INFORMATIONAL BRIEFING - Three Months Out - Group Call |  |  |  | NOTES:
Proposed Dates:
Items arriving mid-March
Staffed pickup days, Sat. March 19 & Sunday March 20
Unstaffed backorder pickup days, April 15-17
Projected Volume:
Last year HVF distributed $70k, 37 participants. TBY distributed $54K, 27 participants. Plan similar to last year, plus or minus 10%
Repeated vendors: Nolts, Progressive Grower, Lakeview, Kreher's, Small Farm Works, Farmers Friend, Bulb crates
Replace Buckhorn, Stanley Paper with 2-3 other vendors
Expect 40-50 pallets per site
Capacity and Planning Questions:
Do we need to cap participation this year?
Is a larger indoor space still a possibility for HVF?
Is it important to keep trying to get supplies to arrive in the week before pickup, or is it ok to have them come earlier?
Anything new we should communicate to drivers?
Proposed Changes
Minor vendor changes - see above
Scheduled backorder day - plan in advance for items to be short; all items after this date refunded
Reduce pickup hours to 1.5 days instead of 2 full weekend days
Supplies: Do you need...
Pallets?
Still have the tarps from last year's order?
Sand bags? (can provide empty ones)
Updated Agreements:
What [project organizer] will do:
Check in 3 times; now; after orders close; 7-10 days out
Make every effort to get items delivered on time in the window we plan together
Gather shipping info: Tell you how many trucks and pallets are coming, their rough delivery window, tracking numbers and contact phone numbers
Provide you with (1) a copy of each order, (2) easy to follow pack-out lists per vendor/item, and (3) an alphabetical list of everybody who's picking up (digital and printed).
Provide a form for collecting information on any shorts or errors.
Provide marking supplies.
Email clear pickup instructions to folks picking up.
Provide a postage-paid mail-back envelope to send back the forms filled out during distribution, OR, pick up the forms at the end of pickup weekend.
Visit each site 1-2 days before pickups to help & problem solve
Compensate you for your work (see below).
What you'll do:
Clear space on the farm for items to arrive and be packed out.
Arrange staffing to break down orders the week before pickup.
Be in contact with the shipping companies as needed to coordinate time of delivery (likely 1 call per vendor).
Count the pallets that arrive and check the bill of lading to make sure it matches the info you were given.
Receive the shipments and unload the pallets with your equipment.
Store weather-sensitive pallets under tarps or in a barn until you're ready to break them down.
Break down pallets from the vendors into individual orders, then check off each order.
Make note of any shorts or errors, and keep the paperwork from getting wet/damaged.
Keep orders with weather-sensitive items tarped or under cover until picked up.
Be prepared to clear snow in the unlikely event of a late March/April snowstorm.
Provide a staff member and loading equipment from 9am-5pm Sat & 9am - 1pm Sun to help load orders.
Explain to the folks with shorts/errors how the shorts/errors will be handled.
Give each farm picking up an "exit ticket" asking for feedback on the bulk order, and collect filled out form.
Mail back or hand-deliver forms to Faith after the pickup day.
Wrap-Up
No-shows: will be encouraged to contact you for an alternate pickup time. They will be charged $10 fee which you will be paid for the extra time.
Unclaimed/extra items: Notify me of these, and we will look for their owner. If they are truly extra, we will collect them or offer them to you.
Follow up feedback: We'd love your input on how this year could be improved upon. We will schedule a call the week after pickup to debrief.
Payment: Checks will be mailed or hand-delivered the week of distribution.
Compensation
A 2.5% commission on sales. For this year, that would look approxiamtely like:
Site 1, $80k in sales, $2000 payment
Site 2, $60k in sales, $1500 payment
OR
For new sites / developing programs: a flat $750 site fee (includes site, use of equipment, and receving orders), plus hourly @ $18.25/hr for assembling orders and staffing pickup weekend. Estimating 1 hour per farm picking up.
ROUND 2: AFTER ORDERS CLOSE - 4 Weeks Out - Group Call or Email |  |  |  | NOTES:
Volume
Number of pickups per site
Total sales, sales per site
Estimated pallets per site
Orders size - average / range
Any other relevant information
Supplies
Pallets?
Tarps - added 1 40x105' tarp to each order
Sand bags? (can provide empty ones)
Shrink Wrap?
FINAL UPDATE - 7-10 Days Out |  |  |  | NOTES:
Info & Supply Kits
I am preparing info & supply kits for you today. I'd like to deliver them to you between today and Monday PM. Let me know if this is OK and if there's anywhere in particular you'd like me to drop them off. They contain:
Pack-out lists for each vendor/item
Pack-out list for each customer
Alphabetical list of pickups
Pickups by pickup time group
Clipboards, sharpies, pallet label paper, and tape to help organize your pack
Some rachet straps and surveyor's tape for the couple folks who may show up unprepared.
Exit ticket surveys for participants to fill out at pickup.
Shorts & errors worksheet to note issues with orders - for you to fill out, for me to resolve
[If paying hourly] An easy form to log your staff time (we'll use it as an invoice to get a check to you)
[If mailing back] Mail-back envelopes for the surveys, shorts list, and time log
Check for site fee (or partial percentage)
Other supplies - confirming you have available
Pallets
Pallet wrap
Tarps
Deliveries / Planned Days / # of Pallets
Almost all delivery dates are still tentative. I will stay in communication as dates/times become final.
Most deliveries should come as planned on Tuesday or Wednesday.
The earliest potential delivery would be Monday afternoon (Vendor)
As of now:
Monday - (Vendors)
Tuesday - (Vendors)
Wednesday - (Vendors)
Thursday - (Vendors)
I've attached a quick-list of the delivery days, estimated # of pallets, and delivery info for each vendor.
Pickups:
About 50% of participants have scheduled a pickup time. I'll give an update by email when I have more complete info. As of now, it's clear that the mornings on both days will be busy, with 2-3 pickups per hour. The afternoons are slower. It's about 60/40 split between Sat and Sun pickups.
Reminder of pick-up site responsibilities:
Count the pallets that arrive and check the bill of lading to make sure they match.
Receive the shipments and unload the pallets with your equipment.
Store weather-sensitive pallets under tarps or in a barn until you're ready to break them down.
Arrange staffing to break down orders between Weds. 3/3 and Friday 3/5.
Break down pallets from the vendors into individual orders, then double check each order.
Make note of any shorts or errors on the form provided.
Keep orders with weather-sensitive items tarped or under cover until picked up.
Provide a staff member and loading equipment from 9am-5pm Sat & Sun to help load orders.
Give farms with shorts/errors the shorts/errors information (to be provided).
Give each farm picking up an "exit ticket" asking for feedback on the bulk order, and collect filled out form.
Mail back filled out forms by 3/31.
Please feel free to call me at any time next week. I know this is a lot of information and I'm happy to repeat or explain any of this by phone, or be available to problem-solve as needed.
DEBRIEF - 1 Week After |  |  |  | NOTES:
What went well?
What were the challenges?
Would you be willing to do it again, and What suggestions do you have for next time?
Thoughts on capacity - too much, room to grow, room to grow under certain circumstances?
Did you need more, different, or better information?
Did you need more, different, or better supplies?

## Budget
BUDGET TEMPLATE
Projected
Revenue
Grant Funds |  |  | 1000
Sales of Farm Supplies |  |  | 150000
| Number of Farm Participants |  | 60
| Average Spending per Farm in Bulk Order Program |  | 2500
| Discount on materials - held as program revenue |  | 6.5%
| Dollar Value of Savings Held as Program Revenue |  | 9750
Total Revenue |  |  | 10750
Program Costs
| Project leader hours | 180 hrs @ $25/hr | 4500 | 3%
| Distribution Fees - Site 1 | 85k, 30 participants | 2125 | 1.417%
| Distribution Fees - Site 2 | 65k, 25 participants | 1625 | 1.083%
| Mileage | 2 visits to each distribution site | 150 | 0.1%
| Bank, CC & ACH fees |  | 750 | 0.5%
| Web Hosting |  | 100 | 0.06667%
| Printing and Supplies |  | 200 | 0.1333%
Fiscal Sponsorship / Adminstrative Fees
Other / Miscellaneous
Total Program Costs |  |  | 9450
Program Development Costs
Legal & Accounting - Business set-up
Outreach
Administrative / Organizational Development
NET |  |  | 1300

## Time & Mileage Tracking
Date | Task | Hours | Mileage | Will this task be required in future years? Y/N | Total Hours: | 0

## Expense Log
Date | Item | Vendor | Receipt (Digital File) | Price | Payment method | Category (References Budget) | Will this expense be required in future years? Y/N | Grant Reimbursable? (Y / N) | Reimbursed?

## Pickup Protocol (hidden)
Thanks for participating in our very first bulk order!
Our vendors are busy getting our orders together, and here's all we need from you now:
Please read through the pickup information below
Please let us know when you plan to arrive, so we can make your pallets accessible. Respond to this email with an estimated arrival time between 9am and 5pm on Saturday or Sunday, (i.e. "Sunday 4pm")
If you ordered Buckhorn bins or hygeine items, check your inbox for a follow-up invoice (prompt payment requested)
Make a plan for transporting your items (and where it'll go when you get back to the farm, of course...)
PICKUP SITE DETAILS
Your pickup site is (FARM NAME, ADDRESS)
Your pickup contact is (NAME), (PHONE), (EMAIL)
Use the entrance indicated on the map and give your site host your order name.
Some items can be loaded with a tractor while others will need to be loaded by hand. Please be prepared to hand load those items.
[OVERHEAD MAP OF PICKUP SITE, ENTRANCE / OTHER NOTABLE ITEMS MARKED]
PLANNING YOUR PICKUP
Please do your best to plan ahead for the volume of items you've ordered. Consider bringing two vehicles or renting a utility trailer for orders with multiple pallets worth of goods.
You can find trailers for rent at Uhaul or Home Depot (links below).
UHaul
Home Depot
Of course, it's always wise to make a plan now for where your items are going after pickup!

## Doc & Link Library
Your Program Information:
program email:
Website [link]
Website editor login [link]
un:
pw:
standard/common use password:
Frequently Used Docs/Links
Order Form [link]
Master Order Sheet [link]
Google Drive Receipts Folder [link]
Template Materials from HV Farm Bulk Order Program:
Public Resources Folder
www.hvfarmbulkorder.com
reach out: hvfarmbulkorder@gmail.com

## Vendor Cold Call Script
Hi there,
I'm a farmer and regular customer in Hudson, New York State. I'm calling because our farm is organizing a bulk purchase program for farms in our area. We are hoping to organize a spring bulk order to reduce shipping and materials costs.
Is there someone I can speak to about arranging a group discount on items and shipping?
[Hold for appropriate staff person]
I'm a farmer and regular customer in New York State. I'm calling because our farm is organizing a bulk purchase program for farms in our area. We are hoping to organize a spring bulk order to reduce shipping and materials costs.
We have about ____#____. producers interested to bulk order your products. We would be looking to compile _____(# of distribution sites)___ orders to be shipped to our distribution sites. I don't yet know exactly how much we'll be ordering, but it's safe to say we'll be ordering at least ($ value) or (# of pallets).
It would be very helpful if you could share any information on discounts available for large orders, both in products and in shipping.
How many pallets? I don't know the answer to that yet, but I think you we can plan for at least 20 pallets.
Distribution site? Please let us know what you require. We are planning for two-three sites on large farms with tractor-trailer turnaround spots and forklifts.
How has this worked for others?
Can we reduce or eliminate shipping costs for these orders?
How would shipping be calculated for an order of this size?
Are there particular volumes ($ or # of items) that would qualify for specific discount rates?
How much lead time would you need to assemble and ship an order of that size? If we gave you our order on __order close date___, could we be guaranteed to receive it on _planned distribution date___?
How would you like to receive the compiled order?
When would you have pricing available / are your current prices still good for February?
How do you ship it out? What would a typical shipping lead time be to our area?

## Materials and Supplies (hidden)
Ordered/Received?
Sharpie Marking Pens
Cardstock for Farm Name Labels
Clipboards
Packing Tape
Printed orders

## Copy of NESARE budget template (hidden)
FNE20-953 | Faith Gilbert, Letterbox Farm
Funding Categories / Item Name | Narrative justification of expense | Unit | Quantity | $ per unit | Quantity x $ =
PERSONNEL Only people employed by the recipient organization or farm should be listed in this category. Those employed elsewhere should be listed under "Other direct costs," or, if individuals are to be paid by another institution via a subaward to that institution, they should be included in a separately detailed subcontract budget and the subcontract total should be listed below under "Subcontracts" in "Other direct costs."
Salaries and wages. Provide narrative detail of each person's role in the project or the services they are providing through their work on the project. Show full-time equivalency as a percentage and salary for each year, or provide hourly wage times number of hours, to equal total $ requested.
Project leader(s).
Faith Gilbert | Project PI, working with Nichki Carangelo on research, developing a Hudson Valley Bulk Supply Framework, piloting Bulk Order Program, and reporting, evaluation and outreach. | Hrs | 185 | 25 | 4625
Nichki Carangelo | Working with Faith Gilbert on research, developing a Hudson Valley Bulk Supply Framework, piloting Bulk Order Program, and reporting, evaluation and outreach. | Hrs | 195 | 25 | 4875
Student wages.
0
Support staff.
Additional staff for distribution sites | Organizing bulk orders and staffing pickup; March 2021 | Hrs | 72 | 20 | 1440
0
Other hired labor.
0
0
Subtotal: Salaries and wages (rounded to the nearest dollar) |  |  |  |  | 10940
Fringe benefits. If applicable, provide the fringe rate that will be applied to wages above and the total for each wage line or category.
0
Subtotal: Fringe benefits (rounded to the nearest dollar) |  |  |  |  | 0
PERSONNEL TOTAL (salaries, hourly labor, and fringe benefits) |  |  |  |  | 10940
NON-PERSONNEL |  | Unit | Quantity | $ per unit | Quantity x $ =
Materials and supplies. Indicate each item with quantity and estimated cost. Include narrative justification on how the item fits the project, its direct need and why not otherwise available through the organization. Items must be project-specific and able to be tracked as being used for the project. General-use items such as office supplies are not allowable unless the items can be tracked and itemized for a project-specific purpose.
Website fees for information page and ordering system | For organizing orders and tracking payments | year | 1 | 250 | 250
Marking Pens, pack of 4 - $6 | For processing bulk order | ea | 1 | 6 | 6
Clipboards - Pack of 6, $15 | For processing bulk order | ea | 1 | 15 | 15
Cardstock for order labels, Pack of 100, $12 | For processing bulk order | ea | 1 | 12 | 12
Packing tape, 4 rolls @ $4.25/roll, $17 | For processing bulk order | roll | 4 | 4.25 | 17
0
Subtotal: Materials and supplies (rounded to the nearest dollar) |  |  |  |  | 300
Travel. For travel of employees/personnel only; list consultant travel under consultants and list conference attendee travel under trainee support. Provide detail as to the destination, purpose of the travel, who is traveling, number of travelers. If a mileage reimbursement, provide miles x rate (not more than federal rate). If lodging, provide rate x number of nights. If travel meals, specify the per diem or allowance to be used.
Mileage for project leaders to distribution site 1 | round trip travel for 1 site visit, 3 days for set up, event, and breakdown; likely distribution site in Hurley, NY | mi | 296 | 0.55 | 162.8
Mileage for project leaders to distribution site 2 | round trip travel for 1 site visit, 3 days for set up, event, and breakdown; confirmed distribution site in Hudson, NY | mi | 64 | 0.55 | 35.2
0
Subtotal: Travel (rounded to the nearest dollar) |  |  |  |  | 198
Publications/printing. Publishing of an article in a scientific or technical journal or other type of field/program related publication or for commercial printing of brochures and program materials. Photocopying costs should be included under "Other direct costs."
0
0
Subtotal: Publications (rounded to the nearest dollar) |  |  |  |  | 0
Other Direct Costs |  | Unit | Quantity | $ per unit | Quantity x $ =
Communications. Mailings, postage, conference calls. Cell phone charges are not allowable.
0
0
Photocopying. In-house photocopying.
0
0
Speaker / trainer fees. Include name, fee, and description of the services they are providing, expenses to be reimbursed, including travel.
0
0
Consultants. Name of those receiving stipends or payments for services and their organization or farm, statement of work or description of what will be done to earn the payment, and breakdown of number of days or hours of service and rate of pay. Provide detail of consultant expenses to be reimbursed such as travel. Add attachment if needed to define the scope of work.
Tax advisor (Sue Baer, CPA) | advice on financial/tax implications of bulk purchase | hr | 2 | 120 | 240
Legal advisor (Jacob Meyer, Esq.) | advice on potential legal entity for bulk purchase | hr | 3 | 75 | 225
Technical Assistance (Megan Galucia) | for 8 hours of advising and 2 hours of webinar participation | hr | 10 | 50 | 500
Webinar Coordinator (NOFA Mass) | 15 hours per webinar @ $17.49/hr | Hrs | 15 | 19.239 | 288.585
PR Coordinator (NOFA Mass) | 5 hours per webinar @ $17.14/hr | Hrs | 5 | 18.854 | 94.27
Services. For non-contracted services rendered for the project. Provide details (fees or hired payments, purpose and quantities).
0
0
Conferences/meetings/workshops. Expenses of holding meetings or training events. Note that travel by employees/personnel should be listed under Travel; travel for presenters under either Consultants or Speakers; and travel for trainee participants under Trainee Support.
Webinar Hosting System, GoTO Webinar | For informational webinar for service providers. $90/month. Two months needed for two sessions. | session | 2 | 90 | 180
0
Trainee support (participant support costs). A subsidy payment to or on behalf of those who receive training, usually for registration fees, lodging, meals, and associated travel. (N.B. Payments for services rendered should be listed above in speaker / trainer fees or consultant payments. Other Conference/meeting/workshop expenses may be listed in that category above.)
0
0
0
0
Off-site office rental. Only allowable if necessary for a project specific purpose.
0
0
Purchase of equipment (or the cost of fabrication of equipment).
0
0
Rental of equipment or land-use charges rental.
Site & equipment use fee for distribution sites | 2 sites, 3 days of warehouse/barn rental; 1 day staffed use of pallet loader or tractor with forks. | flat fee per site | 2 | 750 | 1500
0
Other / miscellaneous. These costs must always be identified in order to be allowed.
|  | ` |  |  | 0
0
|  |  |  | Sum of Other Direct Costs before subcontracts/subawards (rounded to the nearest dollar) | 3028
Subcontracts/Subawards. List the institution, organization or farm. Provide project leader's name and amount of subaward. For each subaward, attach a proposed plan of work and include a spreadsheet of budget detail justification/narrative.
Total from separate spreadsheet:
Total from separate spreadsheet:
|  |  |  | Sum of all subcontracts | 0
Subtotal: Other direct costs (rounded to the nearest dollar) |  |  |  |  | 3028
NON-PERSONNEL TOTAL |  |  |  |  | 3526
TOTAL DIRECT COSTS |  |  |  |  | 14466
Indirect costs. Describe indirect rate or calculations being used, not to exceed the allowed cap, so round down when necessary. Farms and other private businesses should leave the amount blank or enter $0 (see below). |  |  |  |  | 0
TOTAL SARE REQUEST |  |  |  |  | 14466
Acknowledge that indirect has been offered through the application instructions by checking off (X) one of the boxes below.
Indirect is requested, based on the de minimis rate (our organization has never had a federally negotiated indirect cost rate).
Indirect is requested, based on having a federally negotiated indirect cost rate (subject to USDA/NIFA cap of 10% federal funds).
|  |  |  | No indirect is requested. | x
Notice of availability of indirect cost recovery.* Non-profit organizations and academic institutions may be eligible to claim indirect cost recovery as follows: An organization not having a federally negotiated rate for indirect costs, and never having had one previously, may claim up to 10% of modified total direct costs (MTDC) as de minimis to cover overhead.** An organization having a current federally negotiated rate for indirect costs may request indirect up to the USDA/NIFA cap for this program, which currently is 10% of the total SARE request.*** If your organization previously had a federally negotiated rate but it is no longer in effect, your organization is not eligible for indirect funds.****
* Small for-profit businesses (such as commercial farms, veterinary services, private consultants, farm service or product suppliers) receiving SARE awards through UVM will receive vendor service agreements as a contract (rather than a subaward agreement with the flow down of federal regulation) and these service agreements cannot include indirect. Any overhead expenses that can be directly attributable to the grant project may be included in the direct cost budget. ** De minimis. Organizations that have never had a federally negotiated rate agreement may use a de minimis rate of 10% of modified total direct costs (MTDC). MTDC includes all direct costs except for subaward amounts above $25,000 for each subaward organization, and also excludes trainee/participant support costs, long-term rentals, and equipment purchases. *** Current negotiated rate. For institutions having a current federally negotiated rate, to calculate the cap (10% of total funds) divide total direct costs by nine (and round down) or multiply direct costs by 11.11%. **** Ineligible for indirect. Organizations with previously negotiated indirect cost rates that are no longer in effect may not use the previous rate and may not use de minimis, i.e., your organization is not eligible to receive indirect costs.
Form corrected 8-28-2018

## Site Fee Invoice (hidden)
INVOICE FOR SERVICES
Date: | 2021-03-15 | BILL TO:
Program: | Hudson Valley Farm Bulk Order | Letterbox Farm LLC
Contractor Name: | Hawthorne Valley Farm | c/o Faith Gilbert
Address: | 327 Co. Rte. 21c | PO Box 84
City, State, Zip: | Ghent, NY 12075 | Hudson, NY 12534
date of work | description | total
3/15/21 - 3/21/21 | Distribution site fee: for receiving shipments of bulk order supplies; supplying loading equipment; storing supplies; management time in communications with program organizer | 750
750

## Staff Reimbursement Invoice (hidden)
INVOICE FOR SERVICES
Date: | 2021-03-21 |  | BILL TO:
Program: | Hudson Valley Farm Bulk Order |  | Letterbox Farm LLC
Contractor Name: | Tributary Farm |  | c/o Faith Gilbert
Address: | 531 Kyserike Rd |  | PO Box 84
City, State, Zip: | High Falls, NY 12440 |  | Hudson, NY 12534
date of work | description | Hrs | Total
3/15/21 - 3/21/21 | Hours packing individual customer orders for bulk order pickup, @ $18.25/hr