## Project Planner
Building Sustainable Farm Resiliency through Farmer-Centered Business Solutions
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | TEAM MEMBERS RESPONSIBLE | PLAN START (week) | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 2024-04-01 |  |  |  | 2024-05-01 |  |  |  |  | 2024-06-01 |  |  |  |  | 2024-07-01 |  |  |  | 2024-08-01 |  |  |  |  | 2024-09-01 |  |  |  | 2024-10-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  | 2025-03-01 |  |  |  | 2025-04-01 |  |  |  | 2025-05-01 |  |  |  | 2025-06-01 |  |  |  | 2025-07-01 |  |  |  | 2025-08-01 |  |  |  | 2025-06-01 |  |  |  | 2025-07-01 |  |  |  | 2025-08-01 |  |  |  | 2025-09-01 |  |  |  | 2025-10-01 |  |  |  | 2025-11-01 |  |  |  | 2025-12-01 |  |  |  | 2026-01-01 |  |  |  | 2026-02-01 |  |  |  | 2026-03-01
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113
Research Objective 1: Using a farmer-centered approach, perform needs assessment
Obj. 1.1. Establish Farmer Core Team | PIs (Holly, Jay) | 1 | 1 | 1 | 1 | 100%
Obj. 1.2. Develop needs assessment survey | PIs + Farmer Core Team (FCT) (Michelle, Mary, Melissa, Lilian) | 1 | 4 | 0 | 0 | 0%
Obj. 1.3. Perform needs assessment survey | PIs + FCT | 5 | 6 | 0 | 0 | 0%
Obj. 1.4. Hold 3 listening sessions | PIs + FCT | 5 | 6 | 0 | 0 | 0%
Obj. 1.5. Hold 2 focus groups | PIs + FCT | 5 | 6 | 0 | 0 | 0%
Research Objective 2: Synthesize data and develop curriculum materials
Obj. 2.1. Synthesize data and summarize disscussions. | Jay | 11 | 3 | 0 | 0 | 0%
Obj. 2.2. Research existing solutions | PIs + FCT | 14 | 4 | 0 | 0 | 0%
Obj. 2.3. Catalog existing solutions and barriers to access | Jay | 14 | 4 | 0 | 0 | 0%
Obj 2.4. Identify established professionals | PIs + FCT | 14 | 4 | 0 | 0 | 0%
Obj. 2.5. Design curricula frameworks for educational sessions | Jay | 18 | 3 | 0 | 0 | 0%
Research Objective 3: Design educational series to communicate findings in an effective and accessible format
Obj. 3.1. Analyze Objective 1 data for prefered educational methods | Jay | 11 | 3 | 0 | 0 | 0%
Obj. 3.2. Develop proposal for educational sessions | Jay | 20 | 2 | 0 | 0 | 0%
Obj. 3.3. Present proposal to FCT | Jay | 22 | 1 | 0 | 0 | 0%
Obj. 3.4. Revise and finalize sessions | Jay | 23 | 2 | 0 | 0 | 0%
Obj. 3.5. Incorporate Year 1 learnings into Year 2 sessions | Jay | 50 | 33 | 0 | 0 | 0%
Education Objective 1: Create a farmer-friendly resource library to archive learnings
Obj 1.1. Design database | Jay | 16 | 5 | 0 | 0 | 0%
Obj. 1.2. Develop decision making roadmaps | Jay | 20 | 5 | 0 | 0 | 0%
Education Objective 2: Facilitate the peer-to-peer learning network
Obj. 2.1. Invite farmers | PIs + FCT | 24 | 16 | 0 | 0 | 0%
Obj. 2.3. Post events in calendar | Jay | 24 | 4 | 0 | 0 | 0%
Obj. 2.4. Perform direct outreach | Jay, FCT | 24 | 16 | 0 | 0 | 0%
Education Objective 3: Host educational opportunities for farmers
Obj. 3.1. Host 12 events in Year 1 | Jay, FCT | 26 | 20 | 0 | 0 | 0%
Obj. 3.2. Host 12 events in Year 2 | Jay, FCT | 83 | 20 | 0 | 0 | 0%
Education Objective 4: Empower farmers to make better, more efficient business decisions
Obj. 4.1. Post event, update database (repeat in Y2) | Jay | 26 | 20 | 0 | 0 | 0%
Obj. 4.2. Summarize post event surveys (repeat in Y2) | Jay | 26 | 20 | 0 | 0 | 0%
Obj. 4.3. Farmer followup (repeat in Y2) | Jay, FCT | 30 | 20 | 0 | 0 | 0%
Obj. 4.4. Incorporate feedback and new learning into future curriculum | Jay | 50 | 33 | 0 | 0 | 0%