## Sheet1
Task | Year 1, Quarter 1 |  |  | Year 1, Quarter 2 |  |  | Year 1, Quarter 3 |  |  | Year 1, Quarter 4 |  |  | Year 2, Quarter 1 |  |  | Year 2, Quarter 2 |  |  | Year 2, Quarter 3 |  |  | Year 2, Quarter 4 |  |  | Year 3, Quarter 1 |  |  | Year 3, Quarter 2 |  |  | Year 3, Quarter 3 |  |  | Year 3, Quarter 4
| 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01
Develop curriculum and materials for 3 training topics: 1) PPT; 2) Buy-Protect-Sell; and 3) Strategic Land Retirement | bar: 2022-04-01 to 2022-08-01
Develop post-surveys for each of 3 training topics and work with an accredited institution to obtain Institutional Review Board Approval | bar: 2022-09-01 to 2022-12-01
Recruit 2 cohorts of agricultural professional trainees in San Joaquin Valley | bar: 2022-10-01 to 2022-12-01
Logistical planning for PPT trainings in San Joaquin Valley (set dates and times for trainings; secure venues; coordinate with collaborators) | bar: 2022-11-01 to 2023-02-01
Conduct first of two PPT trainings in San Joaquin Valley and administer Western SARE pre-approved survey | bar: 2023-01-01
Analyze Western SARE pre-approved survey results from the first of two PPT trainings in the San Joaquin Valley and adapt subsequent trainings as needed | bar: 2023-01-01 to 2023-02-01
Conduct second of two PPT trainings in San Joaquin Valley and administer Western SARE pre-approved survey | bar: 2023-02-01
Analyze Western SARE pre-approved survey results from the second of two PPT trainings in the San Joaquin Valley and adapt subsequent trainings as needed | bar: 2023-02-01 to 2023-03-01
Recruit 2 cohorts of agricultural professional trainees in Southern California | bar: 2023-04-01 to 2023-06-01
Logistical planning for Buy-Protect-Sell trainings in San Joaquin Valley and Southern California (set dates and times for trainings; secure venues; coordinate with collaborators; inform trainees) | bar: 2023-05-01 to 2023-10-01
Conduct a Buy-Protect-Sell training in San Joaquin Valley and administer Western SARE pre-approved survey | bar: 2023-07-01
Administer online post-survey to San Joaquin Valley trainees for first of two PPT trainings | bar: 2023-07-01
Analyze Western SARE pre-approved survey results from the San Joaquin Valley Buy-Protect-Sell training and adapt subsequent Buy-Protect-Sell trainings as needed | bar: 2023-07-01 to 2023-08-01
Administer online post-survey to San Joaquin Valley trainees for second of two PPT trainings | bar: 2023-08-01
Conduct first of two Buy-Protect-Sell trainings in Southern California and administer Western SARE pre-approved survey | bar: 2023-08-01
Analyze Western SARE pre-approved survey results from the first of two Buy-Protect-Sell trainings in Southern California and adapt subsequent training as needed | bar: 2023-08-01 to 2023-09-01
Conduct second of two Buy-Protect-Sell trainings in Southern California and administer Western SARE pre-approved survey | bar: 2023-10-01
Analyze Western SARE pre-approved survey results from the second of two Buy-Protect-Sell trainings in Southern California and adapt training as needed | bar: 2023-10-01 to 2023-11-01
Logistical planning for Strategic Land Retirement trainings in San Joaquin Valley and Southern California (set dates and times for trainings; secure venues; coordinate with collaborators; inform trainees) | bar: 2023-11-01 to 2024-04-01
Conduct a Strategic Land Retirement training in San Joaquin Valley and administer Western SARE pre-approved survey | bar: 2024-01-01
Administer online post-survey to San Joaquin Valley trainees for the San Joaquin Valley Buy-Protect-Sell training | bar: 2024-01-01
Analyze Western SARE pre-approved survey results from the San Joaquin Valley Strategic Land Retirement training and adapt subsequent trainings as needed | bar: 2024-01-01 to 2024-02-01
Conduct first of two Strategic Land Retirement trainings in Southern California and administer Western SARE pre-approved survey | bar: 2024-02-01
Administer online post-survey to Southern California trainees for first of two Buy-Protect-Sell trainings | bar: 2024-02-01
Analyze Western SARE pre-approved survey results from the first of two Strategic Land Retirement trainings in Southern California and adapt subsequent trainings as needed | bar: 2024-02-01 to 2024-03-01
Conduct second of two Strategic Land Retirement trainings in Southern California and administer Western SARE pre-approved survey | bar: 2024-04-01
Administer online post-survey to Southern California trainees for second of two Buy-Protect-Sell trainings | bar: 2024-04-01
Analyze Western SARE pre-approved survey results from the second of two Strategic Land Retirement trainings in Southern California and adapt subsequent trainings as needed | bar: 2024-04-01 to 2024-05-01
Administer online post-survey to San Joaquin Valley trainees for the San Joaquin Valley Strategic Land Retirement training | bar: 2024-07-01
Administer online post-survey to Southern California trainees for first of two Strategic Land Retirement trainings | bar: 2024-08-01
Administer online post-survey to Southern California trainees for second of two Strategic Land Retirement trainings | bar: 2024-10-01
Analyze survey results and modify curriculum based on analysis | bar: 2024-11-01 to 2025-01-01
Provide follow up resources and guidance to trainees on an ad hoc basis | bar: 2024-02-01 to 2025-03-01