## Project Planner
WSARE Palisade Insectary Biological Control Video Series
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Week Highlight: |  | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PERSON(S) ASSIGNED | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Month | 2023-09-01 |  |  |  | 2023-10-01 | 2023-10-01 |  |  | 2023-11-01 |  | 2023-11-01 |  | 2023-12-01 |  |  |  | 2024-01-01 | 2023-10-01 |  |  | 2024-02-01 |  | 2023-11-01 |  | 2024-03-01 | 2023-10-01 |  |  | 2024-04-01 |  | 2023-11-01 |  | 2024-05-01 | 2023-10-01 |  |  | 2024-06-01 |  | 2023-11-01 |  | 2024-07-01 | 2023-10-01 |  |  | 2024-08-01 |  | 2023-11-01 |  | 2024-09-01 | 2023-10-01 |  |  | 2024-10-01 |  | 2023-11-01 |  | 2024-11-01 | 2023-10-01 |  |  | 2024-12-01 |  | 2023-11-01 |  | 2025-01-01 | 2023-10-01 |  |  | 2025-02-01 |  | 2023-11-01 |  | 2025-03-01 | 2023-10-01
[7 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76
One Page Literature Review for Each Video | Kristi Gladem | 1 | 13 | 0 | 0 | 0%
Storyboard Design for Each Video | Kristi Gladem, Torri Gladem, Dr. Dan Bean | 4 | 16 | 0 | 0 | 0%
Create Narrative Script for Storyboard | Kristi Gladem, Torri Gladem | 4 | 16 | 0 | 0 | 0%
Buy Supplies Needed | Kristi Gladem | 16 | 5 | 0 | 0 | 0%
Complete List of Each Photo and Video Segment Needed | Kristi Gladem, Torri Gladem | 4 | 15 | 0 | 0 | 0%
Agricultural Producer Interviews | Kristi Gladem, Torri Gladem | 21 | 28 | 0 | 0 | 0%
Photography and Videography of Pest Lifestages | Kristi Gladem, Torri Gladem | 28 | 28 | 0 | 0 | 0%
Photography and Videography of Biological Control Lifestages | Kristi Gladem, Torri Gladem | 28 | 28 | 0 | 0 | 0%
Edit Videos Together | Kristi Gladem, Torri Gladem | 56 | 8 | 0 | 0 | 0%
Record Voiceover | Kristi Gladem, Torri Gladem | 56 | 8 | 0 | 0 | 0%
Host Video Critique Workshops | Kristi Gladem, Torri Gladem, Dr. Dan Bean | 64 | 4 | 0 | 0 | 0%
Re-Edit Videos Based on Critiques | Kristi Gladem, Torri Gladem | 66 | 4 | 0 | 0 | 0%
Publish Videos Online | CDA Communication Dept. | 70 | 1 | 0 | 0 | 0%
Promote Videos | Kristi Gladem, Torri Gladem, Dr. Dan Bean, CDA Communications Dept. | 71 | 4 | 0 | 0 | 0%