## Sheet1
Activity | Date
Start Jimmy Nardello Pepper Seeds | Last week of February
Prep experimental Beds in hoop Houses | First week of April
Begin CFPJ Fermentation cycle | 2022-04-06
Apply CFPJ (Demonstration Plot only) | 2022-04-20
Harvest and begin CFPJ fermentation | 2022-04-20
Collect preliminary Soil Samples (1) | Last week of April
Transplant Pepper Seedlings | Last week of April
Apply CFPJ | 2022-05-04
Harvest and begin new CFPJ fermentation | 2022-05-04
Apply CFPJ | 2022-05-18
Harvest and begin new CFPJ fermentation | 2022-05-18
Collect soil samples (2) | 2022-05-19
Send CFPJ to be tested | First week of May
Apply CFPJ | 2022-06-01
Harvest and begin new CFPJ fermentation | 2022-06-01
Apply CFPJ | 2022-06-15
Harvest and begin new CFPJ fermentation | 2022-06-15
Collect soil sample | 2022-06-16
Apply CFPJ | 2022-06-29
Harvest and begin new CFPJ fermentation | 2022-06-29
Install self-guided farm tour | First week of June
Apply CFPJ | 2022-07-13
Harvest and begin new CFPJ fermentation | 2022-07-13
Collect soil samples (3) | 2022-07-14
Apply CFPJ | 2022-07-27
Harvest and begin new CFPJ fermentation | 2022-07-27
Apply CFPJ | 2022-08-10
Harvest and begin new CFPJ fermentation | 2022-08-10
Collect soil samples (4) | 2022-08-11
Apply CFPJ | 2022-08-24
Harvest and begin new CFPJ fermentation | 2022-08-24
Farmer Field Day | First two weeks of September
Apply CFPJ | 2022-09-07
Harvest and begin new CFPJ fermentation | 2022-09-07
Collect Soil Samples (5) | 2022-09-08
Apply CFPJ | 2022-09-21
Harvest and begin new CFPJ fermentation | 2022-09-21
Collect final soil samples (6) | 2022-09-30
Work party | Last two weeks of September
Quivira Coalition Talk | October; date to be coordinated
Quivira Podcast | December; date to be coordinated