## Thyroff Timeline
Emily Thyroff Western SARE Graduate Student Grant - Sustainable Agriculture
|  | 2020 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022
| Task Name | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Objective 1 | Order seedlings and nursery set up | bar: Aug
Nursery measurements | bar: Sep to Feb
Analyze nursery measurements | bar: Oct to May
Destructive sampling | bar: Mar to Apr
Foliar analyses | bar: Apr
Root analyses | bar: Apr to Jul
Outplant remaining seedlings | bar: Apr
Field soil analyses | bar: Apr
Measure outplanted seedlings | bar: Apr; Apr
Final measurement analysis | bar: Apr
Write up | bar: Aug to Apr
Present at TropHTIRC annual meeting | bar: Jan; Jan
Present at conference | bar: Oct
Submit to peer review journal | bar: May to Aug
Share findings/publication on websites | bar: Jul to Aug
Objective 2 | Identify and measure koa crop trees | bar: Sep
Randomly assign overstory treatments | bar: Sep
Order seedlings | bar: Sep
Idenify koa to be thinned | bar: Sep
Thin koa and remove logs from site | bar: Oct
Capture canopy gaps (4 methods) | bar: Oct
Analyze canopy gap capture methods | bar: Oct to Nov
Underplant sandalwood seedlings | bar: Nov
Measure outplanted seedlings | bar: Nov; May; Nov
Physiology measurements | bar: Nov
Create light response curves | bar: Nov to Dec
Analyze measurements | bar: Nov to Jan
Write up | bar: Jan to Jun
Present at TropHTIRC annual meeting | bar: Dec; Jan
Present at conference | bar: Mar
Submit to peer review journal | bar: Jun to Aug
Share findings/publication on websites | bar: Jul to Aug
Outreach | Communication with collaborating producers
Social media presence, skype a scientist
TropHTIRC annual meeting | bar: Jan; Jan
Field site "walk and talk" | bar: Jan; May
Co-write ʻEhunuikamlino school lesson plan | bar: Nov to Jun
Participate in ʻEhunuikamlino school lesson plan | bar: Aug to Jan
ʻEhunuikamlino school field day | bar: Jan
CTAHR Day | bar: Jan; Jan
Guest speaker on podcast | bar: Apr to May
WSARE survey to collaborating producers | bar: Jul; Jul