## Budget items
| WSARE PDP Dome Schools | [5 empty] | Project start: | [7 empty] | 2025-05-01
| Jeff Edwards | Principal Investigator |  |  |  |  | Display week: | [7 empty] | 1
| SIMPLE GANTT CHART by Vertex42.com | [5 empty] | 85774 | 8577.4 | 94351.4
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-04-28 to 2025-06-22
 | time axis 2025-04-28 to 2025-06-22
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
SEE IT (Conference Tour)
| Outline itinerary, Arrange Tour Stops | Jeff Edwards | 0% | 2025-05-01 | 2025-05-31 | 31
| Invite Trainees. Trainees responsible for own flight arrangements to Denver for Arrival July 6th. Confirm participant list and head count | Kerry Richards | 0% | 2025-06-01 | 2025-06-21 | 21
| Reserve travel van | Jeff Edwards | 0% | 2025-06-15 | 2025-06-17 | 3 | 2025-04-29: UW Fleet van rental $170 per day * 5 = $850
| Arange Hotel stays for tour participants | Jeff Edwards | 0% | 2025-06-15 | 2025-06-20 | 6 | 2025-04-28: 0
| Execute Conference/Tour | Jeff Edwards | 0% | 2025-07-07 | 2025-07-12 | 6 | 2025-04-28: 3730; 2025-04-29: See notes on ME&I Calc Tab (5 days per diem 4 nights hotel for Edwards/Richards and 3 trainees)
| Conference Tour Assesment Tool | Kerry Richards | 0% | 2025-07-12 | 2025-07-26
| Track Budget | Edwards, Richards
Dome School Logistics
| Identify local sources for Tools and Supplies | Jeff Edwards in cooperation with local trainees | 0% | 2025-08-01 | 2025-09-30 | 61
| Order non-locally available supplies and ship to dome school locations | Jeff Edwards | 0% | 2025-08-01 | 2025-09-30 | 61
| Confirm Datesand locations for Dome Schools 1-3 | Jeff Edwards in cooperation with local trainees | 0% | 2025-08-01 | 2025-09-30
| Publicize Dome Schools 1-3 and invite local Dome School students | Local trainees1,2,3 | 0% | 2025-09-01 | 2025-09-30 |  | 2025-04-28: 0
| LEARN IT Trainees Dome School #1 (Kona) | [5 empty] | 2025-04-29: 9698
| Travel to #1 dome school location | Edwards, Richards | 0% | 2025-10-01 | 2025-10-03 | 3 | 2025-04-28: 800; 2025-04-29: Airfare - Denver to Kona (1 way $400) and PA to Kona (1 way $400)
| Purchase tools and all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards, Trainee 1 (Kona) | 0% | 2025-10-03 | 2025-10-06 |  | 2025-04-28: 5900; 2025-04-29: Supplies for dome + tools
| Travel to #1 dome school location | Trainees 2 (Maui) and 3 (Guam) | 0% | 2025-10-04 | 2025-10-05 |  | 2025-04-28: 1834; 2025-04-29: Travel from Guam ($1700 RT) and Maui to Kona ($134 RT) for Trainers 2 and 3
| Conduct Dome School #1 | Edwards & Richards | 0% | 2025-10-06 | 2025-10-10 | 5 | 2025-04-28: 7064; 2025-04-29: See notes on ME&I Calc Tab (5 days per diem 4 nights hotel for Edwards/Richards and 2 trainees)
| Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Edwards | 0% | 2025-10-10 | 2025-10-10 | 1 | 2025-04-28: 0; 2025-04-29: covered in line 26
| Order non-locally available supplies and ship to dome school locations | Edwards & Trainees 1, 2, and 3 | 0% | 2025-10-01 | 2025-11-30 |  | 2025-04-29: see above included in line 18
| School #1 Assement Tool | Richards | 0% | 2025-10-10 | 2025-10-20 | 11 | 2025-04-29: time?
| Return to home location | Trainees 2 and 3 | 0% | 2025-10-11 | 2025-10-13 |  | 2025-04-29: see RT airfaare line 24
| Schedule and promote Trainer Dome Schools | Trainees 1, 2, and 3 | 0% | 2025-10-01 | 2025-12-20 |  | 2025-04-28: 0; 2025-04-29: Advertisement $50 per location (3)
| LEARN IT Trainees Dome School #2 (Maui) | [5 empty] | 2025-04-29: 11375
| Travel to #2 dome school location | Edwards, Richards | 0% | 2025-11-01 | 2025-11-03 | 260 | 2025-04-28: 260; 2025-04-29: Travel Kona to Maui 2X130
| Purchase tools and all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards, Trainee 2 | 0% | 2025-11-03 | 2025-11-06 |  | 2025-04-28: 5900; 2025-04-29: Supplies for dome + tools
| Travel to #2 dome school location | Trainees 1 and 3 | 0% | 2025-11-05 | 2025-11-06 |  | 2025-04-28: 1839; 2025-04-29: Travel from Guam ($1700 RT) and Maui to Kona ($139 RT) for Trainees 1 and 3
| Conduct Dome School #2 | Edwards & Richards | 0% | 2025-11-06 | 2025-11-10 |  | 2025-04-28: 9276; 2025-04-29: See notes on ME&I Calc Tab (6 days per diem 5 nights hotel for Edwards/Richards and 2 trainees)
| Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Edwards | 0% | 2025-11-10 | 2025-11-10 |  | 2025-04-28: 0; 2025-04-29: covered in line 34
| School #2 Assement Tool | Richards | 0% | 2025-11-10 | 2025-11-20 |  | 2025-04-28: 0; 2025-04-29: time?
| Return to home location | Trainees 1 and 3 |  | 2025-11-18 | 2025-11-20 |  | 2025-04-28: 0; 2025-04-29: Included in line 34
| LEARN IT Trainees Dome School #3 (Guam) | [5 empty] | 2025-04-29: 12498
| Travel to #3 dome school location | Edwards, Richards | 0% | 2025-12-01 | 2025-12-03 |  | 2025-04-28: 3372; 2025-04-29: Airfare Maui to Guam X2 $1686.00 (1 way)
| Purchase tools and all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards, Trainee 3 | 0% | 2025-12-03 | 2025-12-06 |  | 2025-04-28: 5900; 2025-04-29: Supplies for dome + tools
| Travel to #3 dome school location | Trainees 1 and 2 | 0% | 2025-12-05 | 2025-12-06 |  | 2025-04-28: 3372; 2025-04-29: Travel from Maui and Kona to Guam ($1700 RT) and Trainees 1 and 2
| Conduct Dome School #3 | Edwards & Richards | 0% | 2025-12-06 | 2025-12-10 |  | 2025-04-28: 5754; 2025-04-29: See notes on ME&I Calc Tab (6 days per diem 5 nights hotel for Edwards, Richards and 2 trainees)
| Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Edwards | 0% | 2025-12-10 | 2025-12-10 |  | 2025-04-29: covered in line 43
| Trainee School #3 Assement Tool | Richards | 0% | 2025-12-10 | 2025-12-20 |  | 2025-04-28: 0
| Return to home location | Trainees 1 and 2 |  | 2025-12-18 | 2025-12-20 |  | 2025-04-28: 0; 2025-04-29: included in line 42
| At the conclusion of the 3rd School Trainees Graduate to Trainers | Trainees 1, 2, and 3 |  | 2025-12-10
| TEACH IT Trainer #3 Dome School (Guam) | [5 empty] | 2025-04-29: 3471
| Purchase all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Trainer 3, Edwards, Richards | 0% | 2026-01-03 | 2026-01-05 |  | 2025-04-28: 4900; 2025-04-29: Dome supplies
| Conduct Dome School #1 | Trainer 3, Edwards & Richards | 0% | 2026-01-08 | 2026-01-18 |  | 2025-04-28: 3471; 2025-04-29: See notes on ME&I Calc Tab (6 days per diem 5 nights hotel for Edwards and Richards)
| Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Trainer 3 & Edwards | 0% | 2026-01-18 | 2026-01-20
| Trainer School #3 Assement Tool | Richards | 0% | 2026-01-20 | 2026-01-30
| TEACH IT Trainer #2 Dome School (Maui) | [5 empty] | 2025-04-29: 8010
| Travel to Trainer #2 dome school location | Edwards, Richards | 0% | 2026-02-01 | 2026-02-03 |  | 2025-04-28: 3372; 2025-04-29: Airfare Guam to Maui X2 $1686.00 (1 way)
| Purchase all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards, Trainer 2 | 0% | 2026-02-03 | 2026-02-06 |  | 2025-04-28: 4900; 2025-04-29: Dome supplies
| Conduct Dome School #2 | Trainer 2 & Edwards | 0% | 2026-02-06 | 2026-02-16 |  | 2025-04-28: 4638; 2025-04-29: See notes on ME&I Calc Tab (6 days per diem 5 nights hotel for Edwards and Richards)
| Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Trainer 2 & Edwards | 0% | 2026-02-16 | 2026-02-18
| School #2 Assement Tool | Richards | 0% | 2026-02-18 | 2026-02-28
| TEACH IT Trainer #1 Dome School (Kona) | [5 empty] | 2025-04-29: 4592
| Travel to Trainer #1 dome school location | Edwards, Richards | 0% | 2026-03-01 | 2026-03-03 |  | 2025-04-28: 260; 2025-04-29: Airfare Maui Kona X2 $130 (1 way)
| Purchase all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards, Trainer 1 | 0% | 2026-03-03 | 2026-03-06 |  | 2025-04-28: 4900; 2025-04-29: Dome supplies
| Conduct Dome School #3 | Trainer 1 & Edwards | 0% | 2026-03-06 | 2026-03-16 |  | 2025-04-28: 3532; 2025-04-29: See notes on ME&I Calc Tab (6 days per diem 5 nights hotel for Edwards and Richards)
| Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Trainer 1 & Edwards | 0% | 2026-03-16 | 2026-03-18
| School #2 Assement Tool | Richards | 0% | 2026-03-18 | 2026-03-28
| Return Travel to home location | Edwards, Richards |  | 2026-03-20 |  |  | 2025-04-28: 800; 2025-04-29: Airfare - Denver to Kona (1 way $400) and PA to Kona (1 way $400)
Evaluation
| Progress report Year 1 | Richards, Edwards | 0% | 2026-04-01 | 2026-05-01 | 31
| Update UW Publication B-1322R to reflect pacific island psets and IPM management practices | Edwards | 0% | 2026-04-01 | 2027-04-01 | 366
| Year 2 Project assessment | Edwards, Richards | 0% | 2027-01-01 | 2027-04-30
| Summary SARE Report | Richards, Edwards | 0% | 2027-05-01 | 2027-05-04 | 4
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]

## Sheet1
Project Timeline
TASK | ASSIGNED TO
SEE IT (Conference Tour) |  | UPDATES | Status
Outline itinerary, Arrange Tour Stops | Jeff Edwards | May 2025 - July 2025 | Completed
Invite Trainees. Trainees responsible for own flight arrangements to Denver for Arrival July 6th. Confirm participant list and head count | Kerry Richards | April 2025 Due to federal funding concers tour date reschedule for back up dates August 5 - 7 | Completed
Reserve travel van | Jeff Edwards | 2025-06-01 | Completed
Arange Hotel stays for tour participants | Jeff Edwards | 2025-06-01 | Completed
Execute Conference/Tour | Jeff Edwards | August 5 - 7
Conference Tour Assesment Tool | Kerry Richards
Track Budget | Edwards, Richards | Below budget due to Guam withdawingfrom the no longer attending and teachers return to school | Completed
Dome School Logistics
Identify local sources for Tools and Supplies | Jeff Edwards in cooperation with local trainees | With support from Jose Merianda, Bolton, LLC was identified as a new grower. Bolton generously offered to help source local supplies at their contractor rate. Cooperator Hawaii Western Alternative Learing Support and Services funded the purchase of tools. | Completed
Order non-locally available supplies and ship to dome school locations | Jeff Edwards | For supplies that were not available locally, supplies were sourced from suppliers used with previous dome schools. Since shipping to HI was expensive, those who were flying from the mainland transported the as a second checked bag, thus saving several thousand dollars. | Completed
( | Jeff Edwards in cooperation with local trainees | Dome School # 1 confirmed for ALPSS - December 2025 Dome School #2 Confirmed for Bolton Compost Facility January 3 - 15 Dome School #3 Comfirmed for Hawaii Technical Academy Janiary 16 - January 23 Dome Schools #'s 1,2,3 Final Construction January 24 - January29, Dome School #4 Confirmed for M Farm February 1 - February 4 Dome School #5 Confirmed for Volcano School of the Arts and Sciences Februry 5 -12 | Completed
Publicize Dome Schools 1-3 and invite local Dome School students | Local trainees #1 Ben Duke,AALPS school Local Tainee #2 Jose Mirenda Local Trainee's #3 and #4 Scott Hawaii Technical Academy (HTA) Local Trainee #5 Peggy M Farms | All local trainees publicized the dome scools and recruited participants. Participants for the school dome schools included students, teachers and administrators.
LEARN IT
Dome School #1 ALPSS School Kona |  |  | Completed
Travel to #1 dome school location | Edwards |  | Completed
Purchase tools and all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards,Trainee 1: Ben (ALPSS school Kona) Trainee #2 Jose Miranda | Due to some delays due to shipping, some supplies were not avaialbe in time to conduct dome schools, Therefore, trainers learned some aspects during TEACH IT dome schools. | Completed
Conduct LEARN IT Dome School #1 | Edwards |  | Completed
Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Edwards | This dome school was conducted as part of classroom education, as a result 22 students and educators participated. | Completed
Order non-locally available supplies and ship to dome school locations | Edwards & Richards | Supplies that were not available locally were purchased from suppliers from previous Wyoming dome schools. Due to high shipping costs, some supples were transported as luggage from the mainland which saved thousands of dollars. | Completed
School #1 Assement Tool | Richards | Assessment tool is completed (see attached) not all assessents have been completed. | Tool completed, however, not all assessments have been completed
Schedule and promote Trainer Dome Schools | Local trainees Trainee #1 Ben Duke,AALPS school Tainee #2 Jose Mirenda Trainee's #3 and #4 Scott Hawaii Technical Academy (HTA) Trainee #5 Peggy M Farms | All local trainees publicized the dome scools and recruited participants. Participants for the school dome schools included students, teachers and administrators. | Completed
LEARN IT
Dome School #2 Bolton Comost Facility |  |  | Completed
Travel to #2 dome school location | Edwards, Richards |  | Completed
Purchase tools and all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards, Trainee 2 Jose Miranda | Due to some delays due to shipping, some supplies were not avaialbe in time to conduct dome schools, Therefore, trainers learned some aspects during TEACH IT dome schools. All supplies were delivered, picked up at local suppliers, or transported by Richards and Edwards. | Completed
Conduct Dome LEARN IT School #2 | Edwards & Richards | Dome construction manuals have been distributed to all participants to use as a resource for participantion and future dome construction. | Completed
Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Edwards |  | Completed
School #2 Assement Tool | Richards | Assessment tool is completed (see attached) not all assessents have been completed. | Tool completed, however, not all assessments have been completed
LEARN IT
Dome School #3 Bolton Comost Facility
Purchase tools and all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards, Trainee 2 | Due to some delays due to shipping, some supplies were not avaialbe in time to conduct dome schools, Therefore, trainers learned some aspects during TEACH IT dome schools. All supplies were delivered, picked up at local suppliers, or transported by Richards and Edwards. | Completed
Conduct Dome School #3 | Edwards & Richards | Dome construction manuals have been distributed to all participants to use as a resource for participantion and future dome construction. | Completed
Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Edwards |  | Completed
Trainee School #3 Assement Tool | Richards | Assessment tool is completed (see attached) not all assessents have been completed. | Tool completed, however, not all assessments have been completed
At the conclusion of the 3rd School Trainees Graduate to Trainers | Trainees 1, 2, 3,4,5 |  | Completed
TEACH IT
Dome School #1 Bolton Compost Faciity
ALPSS School and Staff |  |  | Completed
Purchase all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards | Althought there were delays due to shipping, supplies were avaialbe in time to conduct dome schools, All supplies were delivered, picked up at local suppliers, or transported by Richards and Edwards. | Completed
Conduct TEACH IT Dome School #1 | Trainer #1 and Trainer #2 | Over the course of the school 19 students and teachers participated in the school. | Completed
Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Edwards, Richards |  | Completed
TEACH School #1 Assement Tool | Richards | Assessment tool is completed (see attached) not all assessents have been completed. | Tool completed, however, not all assessments have been completed
TEACH IT
Dome School #2 Bolton Comost Facility |  |  | Completed
Hawaii Technical Academy
Purchase all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards, Trainer 2 | Althought there were delays due to shipping, supplies were avaialbe in time to conduct dome schools, All supplies were delivered, picked up at local suppliers, or transported by Richards and Edwards. | Completed
Conduct TEACH IT Dome School #2 | Edwards, Trainers 1,2,3,4,5 |  | Completed
Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Trainer 2 & Edwards | Over the course of the school 25 number of students, and educators participated in the school. Seven teachers and one administrator came out on a Saturday to help consturct the dome shell. | Completed
School #2 Assement Tool | Richards | Assessment tool is completed (see attached) not all assessents have been completed. | Tool completed, however, not all assessments have been completed
TEACH IT
Dome School #3 Bolton Comost Facility |  |  | Completed
Purchase all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards, Trainer 2 | Althought there were delays due to shipping, supplies were avaialbe in time to conduct dome schools, All supplies were delivered, picked up at local suppliers, or transported by Richards and Edwards. | Completed
Conduct Dome School #3 Dome School Location | Edwards, Richards,Trainers 1,2,3,4,5 | Over the course of the school 40 different students,educators, and two community members participated in the school. | Completed
Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Edwards, Trainers #2,, 3, and 5 |  | Completed
School #3 Assement Tool | Richards | Assessment tool is completed (see attached) not all assessents have been completed. | Tool completed, however, not all assessments have been completed
TEACH IT
Dome School #4 H Farm
Travel to TEACH IT Dome School #4 | Edwards, Richards. Trainer 5 |  | Scheduled 2/1 - 2/5
Purchase all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards, Trainer 5 |  | Completed
Conduct TEACH IT Dome School #4 | Edwards, Richards, Trainers 2 and 5 |  | Scheduled 2/1 - 2/5
Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Edwards, Trainers #2,and 5 |  | Scheduled 2/1 - 2/5
TEACH IT
Dome School #5 Volcano School of Arts and Sciences
Travel to TEACH IT Dome School #4 | Edwards, Richards, Trainer 2 |  | Scheduled 2/5 - 2/13
Purchase all remaining supplies, Arrange local supply delivery, verify arrival of shipped supplies, prep school site | Edwards, Richards, Trainer 2 |  | Completed
Conduct Dome School #4 | Edwards, Richards, Trainee 2 |  | Scheduled 2/5 - 2/13
Additional Educational opportunities - repairs, growing in a dome, IPM, Irrigation, etc. | Edwards, Richards, Trainer 2 |  | Scheduled 2/5 - 2/13
Year 1 SARE Report | Richards, Edwards |  | 2026-01-31
Summary SARE Report | Richards, Edwards

## MI&E Calcs
Location |  | Per Diem |  | Hotel |  |  |  | Location | Per Diem | Hotel
Kona |  | 138 |  | 229 |  |  |  | Wyoming | 68 | 110
Maui |  | 122 |  | 354
Guam |  | 99 |  | 159
TRAINEE SCHOOL
Kona | First & Last | Full | Total Days | perdiem | nights | Hotel |  |  | Tour | First & Last | Full | Total Days | perdiem | nights | Hotel
Edwards | 2 | 3 | 5 | 621 | 5 | 1145 |  |  | Edwards | 2 | 3 | 5 | 306 | 4 | 440
Richards | 2 | 3 | 5 | 621 | 5 | 1145 |  |  | Richards | 2 | 3 | 5 | 306 | 4 | 440
Trainee 2 | 2 | 3 | 5 | 621 | 5 | 1145 |  |  | Trainee 1 | 2 | 3 | 5 | 306 | 4 | 440
Trainee 3 | 2 | 3 | 5 | 621 | 5 | 1145 |  |  | Trainee 2 | 2 | 3 | 5 | 306 | 4 | 440
|  |  |  | 2484 |  | 4580 | 7064 |  | Trainee 3 | 2 | 3 | 5 | 306 | 4 | 440
Maui | First & Last | Full | Total Days | perdiem | nights | Hotel
Edwards | 2 | 3 | 5 | 549 | 5 | 1770
Richards | 2 | 3 | 5 | 549 | 5 | 1770 | [6 empty] | 1530 |  | 2200 | 3730
Trainee 1 | 2 | 3 | 5 | 549 | 5 | 1770
Trainee 3 | 2 | 3 | 5 | 549 | 5 | 1770
|  |  |  | 2196 |  | 7080 | 9276
Skin Material
Guam | First & Last | Full | Total Days | perdiem | nights | Hotel |  |  | Sq.ft | Description | Count | rate | Amount
Edwards | 2 | 3 | 5 | 643.5 | 5 | 795 |  |  | 1296 | 36X36 For Dome cover | 6 | 0.27 | 2099.52
Richards | 2 | 3 | 5 | 643.5 | 5 | 795 |  |  | 48 | 6X8 door pieces | 6 | 0.27 | 77.76
Trainee 1 | 2 | 3 | 5 | 643.5 | 5 | 795 |  |  | 400 | 8X50 Vent covers | 6 | 0.27 | 648
Trainee 2 | 2 | 3 | 5 | 643.5 | 5 | 795
|  |  |  | 2574 |  | 3180 | 5754 | [5 empty] | 2825.28 | 470.88
TRAINER SCHOOL | [8 empty] | Pickets
Kona | First & Last | Full | Total Days | perdiem | nights | Hotel |  |  | Unit | Needed per structure | Count | Rate | Amount
Edwards | 2 | 3 | 5 | 621 | 5 | 1145 |  |  | Box of 7 | 6 | 6 | 91 | 3276 | 6101.28 | 546
Richards | 2 | 3 | 5 | 621 | 5 | 1145
|  |  |  | 1242 |  | 2290 | 3532
Maui | First & Last | Full | Total Days | perdiem | nights | Hotel
Edwards | 2 | 3 | 5 | 549 | 5 | 1770
Richards | 2 | 3 | 5 | 549 | 5 | 1770
|  |  |  | 1098 |  | 3540 | 4638
Guam | First & Last | Full | Total Days | perdiem | nights | Hotel
Edwards | 2 | 3 | 5 | 940.5 | 5 | 795
Richards | 2 | 3 | 5 | 940.5 | 5 | 795
|  |  |  | 1881 |  | 1590 | 3471

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.