## Timeline
Item |  | 2023 | [11 empty] | 2024
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Meetings & workshops
1.1 | Regular meetings with producers and range riders
1.2 | Rancher-to-rancher workshops (SARE surveys collected) | bar: 2024 May to 2024 Jun; 2024 Oct to 2024 Nov
2 | Field & Lab Research:
2.1 | Schedule ranch visits to deploy research methods | bar: 2023 Jan to 2023 Jun; 2024 Apr to 2024 May
2.2 | Camera traps deployed (D) & removed (R) | bar: 2023 Mar to 2023 Dec; 2024 Mar to 2024 Dec
2.3 | VHF cattle collars deployed (D) & removed (R) | bar: 2023 Mar to 2023 Dec; 2024 Mar to 2024 Dec
2.4 | Hormone sample collection | bar: 2023 Mar to 2023 Dec; 2024 Mar to 2024 Dec
2.5 | Hormone lab work 2022 and 2023 seasons | bar: 2023 Dec to 2024 Oct
2.6 | Interviews with producers on range riding | bar: 2023 Mar to 2023 Jun; 2024 Mar to 2024 Jul
3 | Data analysis & research dissemination
3.1 | Data coding and analysis
3.2 | Range Rider Toolkit created (C) & distributed (D) | bar: 2023 May to 2024 Dec
Item |  | 2023 Jan: 2025; 2024 Jan: 2026
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Meetings & workshops
1.1 | Regular meetings with producers and range riders | bar: 2025 Jan to 2026 Jul
1.2 | Rancher-to-rancher workshops (SARE surveys collected) | bar: 2025 May
2 | Field & Lab Research:
2.1 | Camera traps deployed (D) & removed (R) | bar: 2025 Mar to 2025 Apr
2.2 | Hormone sample collection | bar: 2025 Mar to 2025 Apr
2.3 | Hormone lab work 2024 season | bar: 2025 Apr to 2025 Jul
3 | Data analysis & research dissemination
3.1 | Data coding and analysis
3.2 | Range Rider Toolkit created (C) & distributed (D) | bar: 2025 Jan to 2025 May
3.3 | Extension Range Rider guide created (C) & distributed (D) | bar: 2025 Nov to 2026 Dec
3.4 | Presentation of findings at conference | bar: 2025 Oct; 2026 Jan
3.5 | 2-3 Peer-reviewed manuscript written and submitted | bar: 2025 Aug to 2026 Dec
3.6 | Two Zoom presentations of findings for project partners | bar: 2026 Apr to 2026 May