## Sheet1
Attachment: Project timeline
Farmers as makers: an inquiry into the viability of developing a MakerSpace in the Albany County hill towns
Tenative Project Timeline (updated 11/4/2014)
| 2015 |  |  | 2015 |  |  | 2015 |  |  | 2016 |  |  | 2016
Project Steps | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June
Project start date |  |  | X
Preparation for outreach/education workshops
Promotion of workshops to farmers and residents
Tentative dates for workshops
Preparation of self-administered questionnaires |  | X
Administer questionnares / upload to web based intrument | [8 empty] | X
Publicity and outreach to residents and farmers
Data Analysis
Final report preparation
Community conference preparation and promotion
Final report completion and dissemination
Community conference tentative date | [13 empty] | X
Appromximate Start Date
Preparation
Active Engagement