|  |  |  |  |
| --- | --- | --- | --- |
| Table 1. 2011 and 2012 completed project activities | | | |
| Date | Year 1 of experiment | Year 2 of experiment | Outreach and Reporting | |
| September 2011 | * Cover crops planted 8/30/12 * Anion resin membranes buried * Baseline soil sampling |  |  | |
| October 2011 | * Soil sampling (inorganic N) |  | * Cover Crop Innovations Field Day | |
| November 2011 | * Soil sampling (biology and inorganic N) * Cover crop biomass sampling * 1st set of resin membranes removed; resin bags buried |  |  | |
| December 2011 | * Soil sampling (inorganic N) |  | * Submitted annual report to SARE | |
| March 2012 | * Soil sampling (inorganic N) |  |  | |
| April 2012 | * Soil sampling (inorganic N) |  |  | |
| May 2012 | * Soil sampling 1 (inorganic N) * Soil sampling 2 (biology and inorganic N) * Cover crop biomass sampling * 2nd set of resin bags removed * Cover crops terminated * Corn planted |  |  | |
| June 2012 | * Soil sampling 1 (inorganic N) * Soil sampling 2 (inorganic N) |  | * Strategies for Soil Health and Nutrient Conservation Field Day | |
| July 2012 | * Soil sampling 1 (inorganic N) * Soil sampling 2 (inorganic N) |  |  | |
| August 2012 | * Soil sampling 1 (inorganic N) * Soil sampling 2 (inorganic N) | * Cover crops planted 8/24/12 * Anion resin bags buried * Baseline soil sampling |  | |
| September 2012 |  | * Soil sampling (inorganic N) |  | |
| October 2012 | * Soil sampling (inorganic N) |  |  | |
| November 2012 | * Corn harvest 11/30/12 | * Soil sampling 2 (biology and inorganic N) * Cover crop sampling * 1st set of resin membranes removed |  | |
| December 2012 |  |  | * Submit annual report to SARE | |