|  |
| --- |
| Table 1. 2011 and 2012 completed project activities |
| Date | Year 1 of experiment | Year 2 of experiment | Outreach and Reporting |
| September 2011 | * Cover crops planted 8/30/12
* Anion resin membranes buried
* Baseline soil sampling
 |  |  |
| October 2011 | * Soil sampling (inorganic N)
 |  | * Cover Crop Innovations Field Day
 |
| November 2011 | * Soil sampling (biology and inorganic N)
* Cover crop biomass sampling
* 1st set of resin membranes removed; resin bags buried
 |  |  |
| December 2011 | * Soil sampling (inorganic N)
 |  | * Submitted annual report to SARE
 |
| March 2012 | * Soil sampling (inorganic N)
 |  |  |
| April 2012 | * Soil sampling (inorganic N)
 |  |  |
| May 2012 | * Soil sampling 1 (inorganic N)
* Soil sampling 2 (biology and inorganic N)
* Cover crop biomass sampling
* 2nd set of resin bags removed
* Cover crops terminated
* Corn planted
 |  |  |
| June 2012 | * Soil sampling 1 (inorganic N)
* Soil sampling 2 (inorganic N)
 |  | * Strategies for Soil Health and Nutrient Conservation Field Day
 |
| July 2012 | * Soil sampling 1 (inorganic N)
* Soil sampling 2 (inorganic N)
 |  |  |
| August 2012 | * Soil sampling 1 (inorganic N)
* Soil sampling 2 (inorganic N)
 | * Cover crops planted 8/24/12
* Anion resin bags buried
* Baseline soil sampling
 |  |
| September 2012 |  | * Soil sampling (inorganic N)
 |  |
| October 2012 | * Soil sampling (inorganic N)
 |  |  |
| November 2012 | * Corn harvest 11/30/12
 | * Soil sampling 2 (biology and inorganic N)
* Cover crop sampling
* 1st set of resin membranes removed
 |  |
| December 2012 |  |  | * Submit annual report to SARE
 |