## Sheet1
Done | Bur Management PERT Chart
Done
Done
Done
Done
Done
Design Fan #1 Exhaust Port
Start:
End: 07/31
Design Fan #1 Vac. Chamber
Start:
End: 07/31
Fabricate Nut Bin Carrier
Start: 08/04
End: 08/15
Fab. Bur Box Trailer
Start: 07/14
End 09/26
Fab. Fan #1 Vac. Chamber
Start: 08/01
End: 08/15
Fab. fan #1 Exaust Port
Start: 08/01
End: 08/15
Reline fan #1 Blower Surface
Start: 08/18
End: 08/22
Design Fan #2 Air Flow Baffel
Start:
End: 07/31
Fab. Fan #2 Air Baffel
Start: 08/01
End: 08/08
Design Fan#2 Exhaust Port
End: 07/31
Fab. Fan #2 Ehaust Port
Start: 08/01
End: 08/22
Air Tests
Start: 08/25
end: 08/25
Fab. Venturi Exhaust Ducts
Start: 08/26
End: 09/26
Field Test & 10/03/2014
Public Demonstration
Start: 09/27
End 10/02/2014
Reinstall Conveyor Belt
Start: 08/22
End: 08/25
Shorten Harvester Length
Start: 07/14
End: 07/29
Install new belt/ test air flow
Start: 06/15
End: 07/14/2014
Prelimary system sketches 01.15/14
Sare Grant Contract 03/31/14
1st Half Sare $ 04/15/14
Order Harvestor Parts 05/01/14
Fabricate Bur Box 05/0 1/14
Design Venturi Exhaust Ducts
Start: 08/01
End: 08/26