## Sheet1
Agroforestry Professional Development Project - Center for Rural Livelihoods | 2023 | [8 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026
Project Schedule (Gantt Chart) | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
TASK 1 - Management
1.1: Award and contracting | bar: 2023 Jul to 2023 Aug
1.2: Annual report | bar: 2024 Mar; 2025 Mar
1.3: Final report | bar: 2026 Feb to 2026 Mar
TASK 2 - Video Development
2.1: Pre-Production Planning
2.1.1: Schedule farm visits and participant interviews | bar: 2023 Jul to 2023 Sep
2.1.2: Develop storyboard | bar: 2023 Aug to 2023 Oct
2.2: Video Production
2.2.1: Filming | bar: 2023 Aug to 2023 Dec; 2024 Apr to 2024 Nov
2.2.2: Editing | bar: 2024 Dec to 2025 Feb
2.2.3: Coding and optimizing for distribution | bar: 2025 Mar
TASK 3 - Webinar Development
3.1: Pre-Production Planning
3.1.1: Develop script and slideshow | bar: 2023 Aug to 2024 Apr
3.1.2: Share to advisory team for edits and feedback | bar: 2024 Apr to 2024 May
3.2: Webinar Production
2.2.1: Filming | bar: 2024 May to 2024 Jun
2.2.2: Editing | bar: 2024 Jul
2.2.3: Coding and optimizing for distribution | bar: 2024 Aug
TASK 4 - Agroforestry Handbook Development
4.1: Collect photos during video production farm visits | bar: 2023 Sep to 2023 Dec; 2024 Apr to 2024 Nov
4.2: Develop first draft of handbook | bar: 2023 Sep to 2024 Sep
4.3: Share to advisory team for edits and feedback | bar: 2024 Sep to 2024 Nov
4.4: Produce final draft of handbook | bar: 2024 Nov to 2025 Mar
TASK 5 - Educational Content Distribution
5.1: Develp and share promotional material | bar: 2025 Feb to 2025 Mar
5.2: Share content with cooperators for distribution | bar: 2025 Mar
5.3: Circulate announcement for webinars and share videos/handbook | bar: 2025 Apr
5.4: Run webinars | bar: 2025 May
TASK 6 - In-Person Field Events
6.1: Finalize field event plan and schedule farm visits
6.2: Develop and share promotional materials for Field Events | bar: 2025 Feb to 2025 Apr
6.3: Host Oregon field event | bar: 2025 Jun
6.4: Host Washington field event | bar: 2025 Oct