## Sheet1
|  |  |  | 44652 | 45275
Tasks
Description | Start Date | End Date | Duration (days)
Lambing | 2022-04-15 | 2022-05-15 | 30
Birth Weight | 2022-04-15 | 2022-04-15 | 30
Pasture | 2022-05-01 | 2022-06-01 | 30
Weigh All | 2022-06-01 | 2022-06-01 | 1
Spring Hill Range | 2022-06-01 | 2022-07-15 | 45
Weigh All | 2022-07-15 | 2022-07-15 | 1
Early Wean | 2022-07-15 | 2022-07-15 | 3
Mountain range | 2022-07-15 | 2022-09-15 | 62
Weigh EW | 2022-07-16 | 2022-07-16 | 1
Weigh EW | 2022-08-01 | 2022-08-01 | 1
Weigh EW | 2022-08-15 | 2022-08-15 | 1
Weigh EW | 2022-09-01 | 2022-09-01 | 1
Wean Twin and Controls | 2022-09-15 | 2022-09-15 | 3
Weigh All | 2022-09-15 | 2022-09-15 | 1
Weigh All | 2022-10-01 | 2022-10-01 | 1
Weigh All | 2022-10-15 | 2022-10-15 | 1
Teaser Rams | 2022-10-15 | 2022-11-01 | 15
Weigh All | 2022-11-01 | 2022-11-01 | 1
Weigh All | 2022-11-15 | 2022-11-15 | 1
Breed | 2022-11-15 | 2022-12-15 | 30
Weigh All | 2022-12-01 | 2022-12-01 | 1
Weigh All | 2022-12-15 | 2022-12-15 | 1
Weigh All | 2023-01-01 | 2023-01-01 | 1
Ultrasound | 2023-01-15 | 2023-01-15 | 1
Lambing | 2023-04-15 | 2023-05-15 | 30
Weigh | 2023-05-15 | 2023-05-15 | 1
Pasture | 2023-05-01 | 2023-06-01 | 30
Weigh | 2023-06-01 | 2023-06-01 | 1
Spring Hill Range | 2023-06-01 | 2023-07-15 | 45
Weigh | 2023-07-15 | 2023-07-15 | 1
Mountain range | 2023-07-15 | 2023-09-15 | 60
Weigh and wean | 2023-09-15 | 2023-09-15 | 1
Analyze Data | 2023-09-15 | 2023-12-15 | 90
Submit final report | 2023-12-15 | 2023-12-15 | 1

## Gantt Data
Description | Start Date | End Date | Duration (days)
Divide animals into treatment groups | 2018-02-15 |  | 1
Feed Treatment 1 diet | 2018-02-15 | 2018-03-15 | 28
First treatment period | 2018-03-16 | 2018-04-05 | 21
Period 1 milk production measure | 2018-04-03 | 2018-04-05 | 3
Period 1 Milk composition collection | 2018-04-04 | 2018-04-05 | 2
Second Treatment period | 2018-04-06 | 2018-04-26 | 21
Period 2 milk production measure | 2018-04-24 | 2018-04-26 | 3
Period 2 Milk composition collection | 2018-04-25 | 2018-04-26 | 2
Third Treatment period | 2018-04-27 | 2018-05-17 | 21
Period 3 milk production measure | 2018-05-15 | 2018-05-17 | 3
Period 3 Milk composition collection | 2018-05-16 | 2018-05-17 | 2
Fourth treatment period | 2018-05-18 | 2018-06-07 | 21
Period 4 milk production measure | 2018-06-05 | 2018-06-07 | 3
Period 4 Milk composition collection | 2018-06-06 | 2018-06-07 | 2
Milk composition analysis | 2018-06-10 | 2018-06-17 | 7
Fatty acid analysis | 2018-06-10 | 2018-07-22 | 35
Data tabulation and analysis | 2018-07-01 | 2018-09-30 | 90
Preparation of meeting material | 2018-10-01 | 2018-11-15 | 45
Preparation of journal manuscript | 2018-11-15 | 2018-02-28 | 105