## Sheet1
2021 Western Farmer/Rancher Grant
Alisha Taff-Rock Front Ranch
ACTIVITY | MILESTONES | PERSON RESPONSIBLE | IMPACT | DATES
Start Date: April 1 2021
Oversight of the Project | sample collection; analyzing data;education | Alisha Taff | Will ensure timely performance and reporting | 4/1/2021 to 9/30/2022
Collecting and Shipping Samples | honey collection; ship samples; get results | Alisha Taff | Results will inform all the educational efforts | 7/2021 and 7/2022
Analyzing Data | get lab results; discuss; record; report | A. Taff; J. Gawenis;M. Greenlief | Records and reporting will improve honey marketing | 8/2021 and 8/2022
Workshop 1 | educate beekeepers; distribute handouts | Alisha Taff | More beekeepers raising bees in California | 2021-05-01
Harvest Day 1 | process and bottle 2 honey crops | Alisha Taff | Improve beekeepers income; more honey on market | July or Aug 2021
Harvest Day 2 | of new beekeepers | Alisha Taff | More high quality California honey on market | July or Aug 2022
Workshop 2 | educate new beekeepers; handouts | Alisha Taff | Beekeepers aquire skills to raise healthy bees | 2022-05-01
Market Honey | Sell new beekeepers honey to RFR stores | Alisha Taff; WIHPA | Improved income for beekeepers; good honey for | Sept 2021 ongoing
consumers
Analyze samples in lab | Receive samples; perform analysis;ship | Dr. James Gawenis | Results will inform all the educational efforts | Sept 2021 and Sept 2022
Write scientific study for peer review | Obtain study results; write study | Dr. Michael Greenlief | Results will impact knowledge of honey components | Aug/Sept 2022
Publish scientific study | Find scientific journal to publish; publish | Dr. Michael Greenlief | Impact knowledge internationally; improve marketing Sept 2022
Educate public | Social media posts; brochures; presentations | WIHPA; Nancy Smith | Better knowledge of public; improved honey sales | ongoing throughout proj.
Educate other beekeepers | Social media posts; manual; presentations | WIHPA; Nancy Smith | Healthier Bees, Better Honey, Increased honey sales | ongoing 1/2022 to
post-project