## Sheet1
Task | Lead | Collaborators | Year 1, Quarter 1 |  |  | Year 1, Quarter 2 |  |  | Year 1, Quarter 3 |  |  | Year 1, Quarter 4 |  |  | Year 2, Quarter 1 |  |  | Year 2, Quarter 2 |  |  | Year 2, Quarter 3 |  |  | Year 2, Quarter 4 |  |  | Year 3, Quarter 1 |  |  | Year 3, Quarter 2 |  |  | Year 3, Quarter 3 |  |  | Year 3, Quarter 4
|  |  | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
Convene Project Advisory Committee | Chantel Welch | Addie Candib; Farm Commons; Knowledge Murpy; Kara Heckert; Greg Plotkin | bar: 2024-05-01; 2024-08-01; 2024-11-01; 2025-02-01; 2025-05-01; 2025-08-01; 2025-11-01; 2026-02-01; 2027-02-01
Develop ToT curriculum | Addie Candib | Chantel Welch Farm Commons; Knowledge Murpy; Kara Heckert; Greg Plotkin | bar: 2024-07-01 to 2024-12-01
Adapt solar leasing guide | Chantel Welch | Farm Commons; Knowledge Murpy; Kara Heckert; Greg Plotkin; Addie Candib | bar: 2024-04-01 to 2024-09-01
Publish ToT Curriculum | Chantel Welch | bar: 2025-07-01
Publish Solar Leasing Guide** | Chantel Welch | bar: 2024-10-01
Recruit cohort | Greg Plotkin | Chantel Welch; Knowledge Murphy; Kara Heckert | bar: 2025-01-01 to 2025-02-01
Offer ToT ** | Addie Candib | Chantel Welch Farm Commons; Knowledge Murpy; Kara Heckert; Greg Plotkin | bar: 2025-03-01 to 2025-05-01
Create online network for ToT participants | Chantel Welch | bar: 2024-11-01 to 2025-01-01
Share content to online network | Knowledge Murphy | Greg Plotkin | bar: 2025-02-01 to 2027-03-01
Quarterly networking & troubleshooting | Knowledge Murphy | Greg Plotkin | bar: 2025-07-01; 2025-10-01; 2026-01-01; 2026-04-01; 2026-07-01; 2026-10-01; 2027-01-01
Survey Administration | Chantel Welch | Knowledge Murphy; Greg Plotkin | bar: 2025-07-01 to 2025-09-01; 2026-06-01 to 2026-08-01
** Milestone