## Gantt
|  |  | Start | End | Duration (hrs./month) | Total Months | Total hours | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023
|  |  | April '22 | October '23 |  |  | 841 | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October
1. Weed Management
Test bed
|  | Ground prep - season start |  |  | 15 | 2 | 30
|  | Lay cardboard |  |  | 15 | 1 | 15
|  | Lay compost |  |  | 25 | 1 | 25
|  | Shape beds |  |  | 5 | 2 | 10
|  | Lay woodchip pathways |  |  | 5 | 2 | 10
|  | Plant transplants |  |  | 5 | 2 | 10
|  | Harvest |  |  | 8 | 10 | 80
Control bed
|  | Ground prep - season start |  |  | 16 | 2 | 32
|  | Shape Beds |  |  | 5 | 2 | 10
|  | Standard soil amendments |  |  | 10 | 2 | 20
|  | Lay straw pathways |  |  | 5 | 2 | 10
|  | Plant transplants |  |  | 5 | 2 | 10
|  | Harvest |  |  | 8 | 10 | 80
Monitoring
|  | Qualitative visual monitoring (pests/health etc.) |  |  | 1 | 12 | 12
|  | Quadrat density survey |  |  | 1 | 12 | 12
|  | Test Bed - Timed Weeding (Hori Hori) |  |  | 15 | 12 | 180
|  | Control Bed - Timed Weeding (Stirrup Hoe) |  |  | 17 | 12 | 204
2. Soil Health
Soil samples at beginning and end of the project duration in each bed (test and control)
|  | Collect samples |  |  | 3 | 2 | 6
|  | Ship samples |  |  | 0.5 | 2 | 1
|  | Samples in lab |  |  |  |  | 0
|  | Results |  |  |  |  | 0
3. Profitability/Yield/Productivity
| Collect weekly harvest weight (total per row for control & test beds of Kale) |  |  |  | 1 | 12 | 12
| Weekly note of diseases/plant distress - photos when appropriate |  |  |  | 1 | 12 | 12
| Weekly calculation of hours spent weeding |  |  |  | 1 | 12 | 12
4. Documentation and Educational Material Development
| Preparing and hosting classes, documenting results |  |  |  | 4 | 12 | 48