## Sheet1
Task/Activity | Start date | Finish date | Duration | Range | Start date | Finish date | Duration
Statewide producer interviews: goals/objectives/barriers | 2020-08-01 | 2021-03-01 | 210 | 2021-03-01
Anlysis of interview data | 2021-04-01 | 2021-08-01 | 150 | 2021-09-01
Assess ecological and sociological impacts of silvopasture | 2020-08-01 | 2022-08-01 | 750 | 2022-08-01
Initial assessment of on-farm research sites with current practitioners | 2020-08-01 | 2021-04-17 | 275 | 2021-02-17
Conduct field research with current practitioners | 2021-05-01 | 2022-08-01 | 450
Establish research plots (assess fuel loads, soil compaction, forage quality) | 2021-05-01 | 2021-05-31 | 30
Line intercept transects (assess stand composition and structure) | 2021-05-01 | 2022-05-01 | 250 | 2020-12-01
Assess barriers to silvopasture establishment/maintenance | 2020-08-01 | 2022-08-15 | 750 | 2021-02-01
On-Farm Educational Farm Walk Event #1 | 2022-06-01 | 2022-06-01 | 10 | 2021-03-01
On-Farm Educational Farm Walk Event #2 | 2022-07-01 | 2022-07-01 | 10
Draft and Submit WSU extension bulletin | 2022-05-01 | 2022-12-01 | 200 | 2022-12-01
Ecological data analysis | 2022-03-01 | 2022-06-01 | 150 | 2021-06-01
Final WSARE Project Report | 2022-08-15 | 2022-10-15 | 75 | 2022-08-01
Initial and Quarterly Leadership Team Zoom Meetings | 2020-08-01 | 2022-08-15 | 900 | 2022-10-15