## Sheet1
| 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26
Tasks | Spr | Sum | Fall | Win | Spr | Sum | Fall | Win | Spr | Sum | Fall | Win
Project Planning and Setup
Initial meetings with producers | X
Project Meetings with Ranchers |  |  | X |  |  |  | X |  |  |  | X
Implement Mgmt Practices
Establish plots at PMC | X
irrigation of PMC plots |  | X | X |  | X | X | X |  | X | X | X
Establish plots on ranches |  |  |  |  | X
Irrigation of ranch plots | [5 empty] | X | X |  | X | X | X
Data Collection and Analysis
Sampling of PMC plots |  | X | X |  | X | X | X |  | X | X | X
Sampling of ranch plots |  |  |  |  | X | X | X |  | X | X | X
Outreach, Extension, and Evaluation
Social media | X | X | X | X | X | X | X | X | X | X | X | X
Newsletters/UC Delivers |  |  | X |  |  |  | X |  |  |  | X
Popular press articles & peer reviewed paper | [11 empty] | X
Video summary of project | [9 empty] | X | X
On-farm field days |  |  | X |  |  |  | X |  | X |  | X | X
Presentations at industry meetings | [7 empty] | X |  |  |  | X
Grower feedback on project/practices | [10 empty] | X | X