## Sheet1
Objective | Activities | 2023 | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | 2024 | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | 2025 | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
R1, R2 | Acquire cover crop seed and tools | bar: Jan to March
R1, R2 | Preplanting research: determine seeding rates and other needs of each crop | bar: Jan to March
R1, R2 | Assign replicates to subplots within study area | bar: Jan to March
R1, R2 | Plant cover crop plots | bar: May
R1 | Sticky card insect sampling at biweekly intervals | bar: May to Oct
R1 | Sweep sampling at biweely intervals | bar: May to Oct
R1 | Identify and record insects from sticky card and sweep sampling | bar: Nov to Dec
R2 | Weekly agronomic observations in cover crop plots | bar: May to Oct
R2 | Perform soil tests and send samples for analysis | bar: May; Oct
R2 | Harvest and dry biomass samples, calculate biomass for each | bar: Aug to Nov
R1, R2 | Terminate cover crop plots, basing termination date on when each begins to go to seed and timing termination before this occurs | bar: Aug to Oct
R1, R2 | Insect and cover crop data analysis | bar: Dec
E3 | Make educational posts about project design, goals and outcomes to Brown Dog Farm Instagram page | bar: March; June; Sept; Dec
E1, E2 | Prepare materials for onsite demonstration day, including initial findings from Year 1 trials and participant pre-post survey
E1, E2 | Advertise and open registration for onsite demonstration day
E1, E2 | Host onsite demonstration day for local farmers and agricultural technicians
R1, R2, E1, E2 | Determine final results of research and prepare for presentation at agricultural conference and publication in online project summary
E1, E2 | Presentation of results at regional agricultural conference
E1, E2 | Distribute pre-post and grower interest surveys
E1, E2 | Follow-up with interested growers to gauge interest, encourage use of cover crop plots, and offer technical advice
E1, E2 | Send follow-up surveys to determine which participants of previous outreach activities included cover crop plots on their own farms
E1, E2 | Prepare online project summary on Brown Dog Farm website
E1, E2 | Publish online project summary on Brown Dog Farm website
R1, R2, E1, E2, E3 | Annual progress reporting
R1, R2, E1, E2, E3 | Project Evaluation and final reporting