## Sheet1
Objective | Activity | 2021 |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024
|  | Apr-June | July-Sept | Oct-Dec | Jan-Mar | Apr-June | July-Sept | Oct-Dec | Jan-Mar | Apr-June | July-Sept | Oct-Dec | Jan-Mar
Research | Project starts on April 1, 2021 to facilitate dog training | X
Research | Dog+handler teams training in weekly sessions | XXX |  | XXX |  | XXX |  | XXX | XXX |  |  |  | XXX
Research | Dog+handler teams and trappers practice trapping-day coordination |  |  | XXXXXXX
Research | Dog teams accompany trappers to set traps on farms |  |  |  | XXXXXXX | XXXXXXX |  |  | XXXXXXX | XXXXXXX
Research | Human-only trappers locate and set traps on control plots on farms |  |  |  | XXXXXXX | XXXXXXX |  |  | XXXXXXX | XXXXXXX
Research | Analyze between-treatment trap effectiveness data, weekly capture trends, and inter-team metrics | [5 empty] | XXXXXXX |  |  |  | XXXXXXX
Research | Convene dog+handler teams, trappers, farmers, Pis, and canine consultant to review data and adjust approaches | [6 empty] | XXXXXXX |  |  |  | XXXXXXX
Research | Analyze intra- and inter-year results of trapping effectives, capture trends, and intra- and inter-team metrics | [9 empty] | XXXXXXX
Research | Submit journal article for publication | [11 empty] | XX
Education | Coordinte OSU Extension Rodent Management working group | XXX |  |  | XXX |  |  |  | XXX |  |  |  | XXX
Education | Host field days |  |  |  | XXX |  |  |  | XXX
Education | Distribute content on the project blog |  |  |  | XXXXXXX | XXXXXXX |  |  | XXXXXXX | XXXXXXX |  |  | XXXXXXX
Education | Publish newsletter articles about the project |  |  |  |  | XXXXXXX |  |  |  | XXXXXXX
Education | Present project findings at farmer conferences | [7 empty] | XXX |  |  |  | XXX
Education | Publish new Extension Publication | [11 empty] | XXX
Education | Finalize canine vole scent detection guidelines | [8 empty] | XXX
General | Final report to WSARE | [11 empty] | XX