## Sheet1
Activity/Milestone | Prior | 2020 | [8 empty] | 2021 | [12 empty] | 2022 | [12 empty] | 2023 |  |  | Post
|  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Collect earwigs
Recruit student
Team meeting | bar: Oct
Professional Conference Presentation by Student | [7 empty] | Nov: ESA, Obj. 1; 2021 Apr: PB-ESA, Obj. 2 | [6 empty] | ESA, Obj. 2 |  | Orchard Pest Manag Disease Conf, Obj. 1-2 |  |  | PB-ESA, Obj. 3 | [9 empty] | Orchard Pest Manag Disease Conf, Obj. 3
Paper submission | [26 empty] | Obj. 1 - J. Econ Entomol. | [10 empty] | Obj. 2 - Biol. Control | Obj. 3 - Pest Mang. Sci. | Obj. 4 - J. IPM case study
Obj. 1
1ab. Establish plots
1ab. Deploy & monitor traps | bar: 2021 May
1b. Fruit damage assessment
1ab. Data/econ analysis
Obj. 2
2a. No-choice tests
2a. Choice tests
2a. Analyze Data | bar: Oct
2b. Early releases, apple
2b. Late releases, apple
2b. Monitoring, apple | bar: 2021 May
2b. Releases, pear
2b. Monitor earwigs, pear
2ab. Fruit damage assessment
2c. Deploy shelters
2c. Sample for earwigs
2d. Releases by hand & drone
2d. Monitor for marked earwigs
2d. Test marked earwigs
2d. Monitor earwigs via counts
2b-c. Final data/econ analysis
Obj. 3
Conduct assays
Final Data Analysis
Obj. 4
Website | Design |  |  | Update |  |  | Update | Dec: Update; 2021 Mar: Update |  | Update |  |  | Update |  |  | Update |  |  | Update |  |  | Update |  |  |  | Update |  |  | Update |  |  | Update
Survey
Extension articles | [23 empty] | PNW extension bulletin | WSU Fruit Matters | [9 empty] | Update OPM earwig article |  | PNW extension bulletin | WSU Fruit Matters | Good Fruit Grower
Grower meeting presentations | [22 empty] | NCW Pear Day + others | [12 empty] | Hood River Co. Hort Meeting + others
Field Days | [29 empty] | Stutzman/Nottingam | Hunt/Thompsen
Assess grower implementation | bar: 2021 Jan

## Sheet2
Group responsible
USDA, Wapato
WSU, Wenatchee
OSU, Hood River
OSU, Medford
USDA, Maricopa
M3 Consulting
PNW collaborators
All