## Sheet1
Timeline for Establishing a Cool Season Legume Grass Finishing Pasture
Name/Yr | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
Jess/22 | Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Apr: Till & Seed; Timeline for Establishing a Cool Season Legume Grass Finishing Pasture June: Sample at Stanford.; Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Sept: Sample at Stanford.
Ryan/22 | Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Apr: Till & Seed; Timeline for Establishing a Cool Season Legume Grass Finishing Pasture June: Sample at Marion.; Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Sept: Sample at Marion.
Pete/22 | Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Apr: Till & Seed; Timeline for Establishing a Cool Season Legume Grass Finishing Pasture June: Sample at Stanford, Marion, Kila; Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Sept: Sample at Kila.
Jack/22 | Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Apr: Available for questions from others and any assistance that may be required throughout the year.
Lisa/22 | Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Apr: No responsibilities this year.
Jess/23 | Timeline for Establishing a Cool Season Legume Grass Finishing Pasture June: Sample at Stanford.; Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Oct: Tour at Stanford.
Ryan/23 | Timeline for Establishing a Cool Season Legume Grass Finishing Pasture June: Sample at Marion.; Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Oct: Tour at Marion.
Pete/23 | Timeline for Establishing a Cool Season Legume Grass Finishing Pasture June: Sample at Kila.; Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Aug: Obtain all results & invite guests.
Jack/23 | Jan: Available for questions from others and any assistance that may be required throughout the year.; Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Oct: Coordinate with Lisa re: presentation.
Lisa/23 | Timeline for Establishing a Cool Season Legume Grass Finishing Pasture Aug: Obtain results from Pete, prepare, & present results.
Lisa/24 | Jan: Coordinate postings of results to websites.
Pete/24 | Jan: Prepare final report & submit to SARE.