## Product planning
Social network analysis of organic seed systems Project Timeline
Lubell, Wood, Zystro, Brijette Peña, Beth Rasgorshek, Karl Sutton
Task | Start Date | End Date | Team
O1: Survey development | 2020-08-01 | 2020-08-31 | Wood, Zystro, Lubell, Peña, Rasgorshek, Sutton
O1: Survey administration | 2020-10-01 | 2022-09-01 | Wood & Zystro
O2: Preliminary survey analysis | 2020-11-16 | 2021-01-31 | Wood & Lubell
O2: Ongoing survey analysis | 2021-02-01 | 2022-09-30 | Wood
O3: Participatory review workshop |  | 2022-02-01 | Wood
O4: State of Organic Seed (SOS) Report write-up | 2021-10-01 | 2022-02-01 | Wood & Zystro
O4: Submit SOS Report |  | 2022-02-01 | Wood & Zystro
O4: Preparation of final presentations |  |  | Wood & Zystro
O4: Summit and Conference presentations |  | 2022-02-01 | Wood & Zystro
O4: Preparation of academic manuscript | 2022-03-01 | 2022-12-01 | Wood & Lubell
O4: Submit manuscript draft |  | 2022-12-15 | Wood & Lubell